## Risk Chart
Geometric Risk |  |  |  |  | Arithmetic Risk
Design Option | Duration | Criticality Risk | Activity Risk | Fibonacci Risk | Criticality Risk | Activity Risk | Fibonacci Risk
Simulators | 7.1333 | 0.71624 | 0.91269 | 0.68779 | 0.80556 | 0.75661 | 0.78986
Infra+Clients Front End | 7.8333 | 0.71784 | 0.92796 | 0.64444 | 0.77174 | 0.80978 | 0.72495
TopDev1+ TopDev2 | 8.5333 | 0.72292 | 0.92796 | 0.66201 | 0.78571 | 0.80272 | 0.74372
TopDev2 | 9.4667 | 0.62139 | 0.93187 | 0.5639 | 0.70238 | 0.77489 | 0.65972
Normal | 9.9333 | 0.64585 | 0.94373 | 0.59035 | 0.72619 | 0.79487 | 0.6822
D4 | 10.4 | 0.42393 | 0.7871 | 0.34851 | 0.45238 | 0.53931 | 0.36971
D3 | 10.8667 | 0.39685 | 0.70292 | 0.3329 | 0.42857 | 0.44654 | 0.35582
D2 | 12.0333 | 0.26706 | 0.57891 | 0.25287 | 0.28571 | 0.3261 | 0.27245
D1 | 13.4333 | 0.26706 | 0.49846 | 0.25287 | 0.28571 | 0.26701 | 0.27245
Z1 | 14.4 | 0.29 | 0.22
Z2 | 15.9 | 0.29 | 0.25
D3
D4
Normal

## Risk Model
Coefficients | Direct Cost | Geometric Risk | Solver: | Risk
a | 0.98971 | 0.0066739 | 8.315 | 0.97113 | Max Risk
b | -21.3173 | -0.21895
c | 136.5684 | 2.2569
d |  | -6.4934
Duration | Direct Cost | Geometric Risk Model
6 | 44.2945 | 0.60713
6.1 | 43.3603 | 0.64117
6.2 | 42.4459 | 0.67327
6.3 | 41.5513 | 0.70348
6.4 | 40.6765 | 0.73184
6.5 | 39.8215 | 0.75837
6.6 | 38.9863 | 0.78313
6.7 | 38.1709 | 0.80616
6.8 | 37.3753 | 0.82749
6.9 | 36.5995 | 0.84716
7 | 35.8434 | 0.86522
7.1 | 35.1072 | 0.8817
7.2 | 34.3908 | 0.89664
7.3 | 33.6941 | 0.91009
7.4 | 33.0173 | 0.92208
7.5 | 32.3602 | 0.93266
7.6 | 31.7229 | 0.94186
7.7 | 31.1055 | 0.94973
7.8 | 30.5078 | 0.9563
7.9 | 29.9299 | 0.96161
8 | 29.3718 | 0.96571
8.1 | 28.8335 | 0.96864
8.2 | 28.315 | 0.97042
8.3 | 27.8163 | 0.97112
8.4 | 27.3374 | 0.97075
8.5 | 26.8783 | 0.96938
8.6 | 26.439 | 0.96702
8.7 | 26.0195 | 0.96373
8.8 | 25.6197 | 0.95955
8.9 | 25.2398 | 0.95451
9 | 24.8797 | 0.94865
9.1 | 24.5393 | 0.94203
9.2 | 24.2188 | 0.93466
9.3 | 23.918 | 0.9266
9.4 | 23.637 | 0.91789
9.5 | 23.3759 | 0.90856 | Second derivative zero | 10.9357
9.6 | 23.1345 | 0.89865
9.7 | 22.9129 | 0.88821
9.8 | 22.7111 | 0.87728
9.9 | 22.5291 | 0.86589
10 | 22.3669 | 0.85409
10.1 | 22.2245 | 0.84191
10.2 | 22.1019 | 0.8294
10.3 | 21.9991 | 0.81659
10.4 | 21.916 | 0.80353
10.5 | 21.8528 | 0.79025
10.6 | 21.8094 | 0.7768
10.7 | 21.7857 | 0.76321
10.8 | 21.7819 | 0.74953
10.9 | 21.7978 | 0.7358
11 | 21.8336 | 0.72205
11.1 | 21.8891 | 0.70833
11.2 | 21.9644 | 0.69467
11.3 | 22.0596 | 0.68112
11.4 | 22.1745 | 0.66772
11.5 | 22.3092 | 0.6545
11.6 | 22.4637 | 0.6415
11.7 | 22.638 | 0.62878
11.8 | 22.8321 | 0.61636
11.9 | 23.046 | 0.60428
12 | 23.2797 | 0.59259
12.1 | 23.5331 | 0.58133
12.2 | 23.8064 | 0.57053
12.3 | 24.0995 | 0.56024
12.4 | 24.4123 | 0.5505
12.5 | 24.745 | 0.54134
12.6 | 25.0974 | 0.53281
12.7 | 25.4697 | 0.52495
12.8 | 25.8617 | 0.51779
12.9 | 26.2735 | 0.51138
13 | 26.7052 | 0.50575
13.1 | 27.1566 | 0.50096
13.2 | 27.6278 | 0.49702
13.3 | 28.1188 | 0.494
13.4 | 28.6296 | 0.49192
13.5 | 29.1602 | 0.49083
13.6 | 29.7106 | 0.49077
13.7 | 30.2808 | 0.49177
13.8 | 30.8707 | 0.49388
13.9 | 31.4805 | 0.49713
14 | 32.1101 | 0.50158
14.1 | 32.7594 | 0.50725
14.2 | 33.4286 | 0.51419
14.3 | 34.1175 | 0.52243
14.4 | 34.8263 | 0.53202
14.5 | 35.5548 | 0.543
14.6 | 36.3032 | 0.55541
14.7 | 37.0713 | 0.56928
14.8 | 37.8592 | 0.58466
14.9 | 38.6669 | 0.60159
15 | 39.4944 | 0.62011

## Risk Model to Scale
|  |  | TMR | 8.315
|  |  | R(TMR) | 0.97113
|  |  | C(TMR) | 27.7432
|  |  | F | 28.5679
Duration | Direct Cost | Geometric Risk Model
6 | 44.2945 | 17.3443
6.1 | 43.3603 | 18.3168
6.2 | 42.4459 | 19.234
6.3 | 41.5513 | 20.0971
6.4 | 40.6765 | 20.9071
6.5 | 39.8215 | 21.6652
6.6 | 38.9863 | 22.3726
6.7 | 38.1709 | 23.0303
6.8 | 37.3753 | 23.6396
6.9 | 36.5995 | 24.2016
7 | 35.8434 | 24.7175
7.1 | 35.1072 | 25.1883
7.2 | 34.3908 | 25.6153
7.3 | 33.6941 | 25.9995
7.4 | 33.0173 | 26.3421
7.5 | 32.3602 | 26.6442
7.6 | 31.7229 | 26.9071
7.7 | 31.1055 | 27.1318
7.8 | 30.5078 | 27.3195
7.9 | 29.9299 | 27.4713
8 | 29.3718 | 27.5884
8.1 | 28.8335 | 27.672
8.2 | 28.315 | 27.723
8.3 | 27.8163 | 27.7428
8.4 | 27.3374 | 27.7324
8.5 | 26.8783 | 27.6931
8.6 | 26.439 | 27.6258
8.7 | 26.0195 | 27.5319
8.8 | 25.6197 | 27.4123
8.9 | 25.2398 | 27.2684
9 | 24.8797 | 27.1011
9.1 | 24.5393 | 26.9117
9.2 | 24.2188 | 26.7013
9.3 | 23.918 | 26.4711
9.4 | 23.637 | 26.2221
9.5 | 23.3759 | 25.9556
9.6 | 23.1345 | 25.6727
9.7 | 22.9129 | 25.3744
9.8 | 22.7111 | 25.0621
9.9 | 22.5291 | 24.7367
10 | 22.3669 | 24.3995
10.1 | 22.2245 | 24.0516
10.2 | 22.1019 | 23.6941
10.3 | 21.9991 | 23.3282
10.4 | 21.916 | 22.9551
10.5 | 21.8528 | 22.5758
10.6 | 21.8094 | 22.1915
10.7 | 21.7857 | 21.8034
10.8 | 21.7819 | 21.4126
10.9 | 21.7978 | 21.0203
11 | 21.8336 | 20.6275
11.1 | 21.8891 | 20.2355
11.2 | 21.9644 | 19.8454
11.3 | 22.0596 | 19.4582
11.4 | 22.1745 | 19.0753
11.5 | 22.3092 | 18.6976
11.6 | 22.4637 | 18.3265
11.7 | 22.638 | 17.9629
11.8 | 22.8321 | 17.608
11.9 | 23.046 | 17.2631
12 | 23.2797 | 16.9292
12.1 | 23.5331 | 16.6074
12.2 | 23.8064 | 16.299
12.3 | 24.0995 | 16.005
12.4 | 24.4123 | 15.7267
12.5 | 24.745 | 15.4651
12.6 | 25.0974 | 15.2214
12.7 | 25.4697 | 14.9967
12.8 | 25.8617 | 14.7922
12.9 | 26.2735 | 14.609
13 | 26.7052 | 14.4483
13.1 | 27.1566 | 14.3113
13.2 | 27.6278 | 14.199
13.3 | 28.1188 | 14.1125
13.4 | 28.6296 | 14.0532
13.5 | 29.1602 | 14.022
13.6 | 29.7106 | 14.0202
13.7 | 30.2808 | 14.0488
13.8 | 30.8707 | 14.1091
13.9 | 31.4805 | 14.2021
14 | 32.1101 | 14.3291
14.1 | 32.7594 | 14.491
14.2 | 33.4286 | 14.6892
14.3 | 34.1175 | 14.9248
14.4 | 34.8263 | 15.1988
14.5 | 35.5548 | 15.5125
14.6 | 36.3032 | 15.8669
14.7 | 37.0713 | 16.2632
14.8 | 37.8592 | 16.7026
14.9 | 38.6669 | 17.1863
15 | 39.4944 | 17.7152

## Crossover
Solver:
|  |  |  | Duration | Risk - Cost Derivative Formula | Risk
|  |  |  | 9.4354 | 1.2308e-08 | 0.91466
|  |  |  | 12.2527 | -1.7623e-07 | 0.56504
Duration | Direct Cost Derivative | Geometric Risk Derivative
6 | 9.4407 | 10.0056 | 0.56487
6.05 | 9.3418 | 9.7247 | 0.38296
6.1 | 9.2428 | 9.4467 | 0.20391
6.15 | 9.1438 | 9.1715 | 0.027724
6.2 | 9.0448 | 8.8992 | -0.1456
6.25 | 8.9459 | 8.6298 | -0.31607
6.3 | 8.8469 | 8.3632 | -0.48368
6.35 | 8.7479 | 8.0995 | -0.64843
6.4 | 8.649 | 7.8386 | -0.81032
6.45 | 8.55 | 7.5806 | -0.96935
6.5 | 8.451 | 7.3255 | -1.1255
6.55 | 8.352 | 7.0732 | -1.2788
6.6 | 8.2531 | 6.8238 | -1.4293
6.65 | 8.1541 | 6.5772 | -1.5769
6.7 | 8.0551 | 6.3335 | -1.7216
6.75 | 7.9562 | 6.0927 | -1.8635
6.8 | 7.8572 | 5.8547 | -2.0025
6.85 | 7.7582 | 5.6196 | -2.1386
6.9 | 7.6593 | 5.3873 | -2.2719
6.95 | 7.5603 | 5.1579 | -2.4023
7 | 7.4613 | 4.9314 | -2.5299
7.05 | 7.3623 | 4.7077 | -2.6546
7.1 | 7.2634 | 4.4869 | -2.7765
7.15 | 7.1644 | 4.2689 | -2.8955
7.2 | 7.0654 | 4.0538 | -3.0116
7.25 | 6.9665 | 3.8416 | -3.1249
7.3 | 6.8675 | 3.6322 | -3.2353
7.35 | 6.7685 | 3.4257 | -3.3428
7.4 | 6.6695 | 3.222 | -3.4475
7.45 | 6.5706 | 3.0212 | -3.5493
7.5 | 6.4716 | 2.8233 | -3.6483
7.55 | 6.3726 | 2.6282 | -3.7444
7.6 | 6.2737 | 2.436 | -3.8377
7.65 | 6.1747 | 2.2466 | -3.9281
7.7 | 6.0757 | 2.0601 | -4.0156
7.75 | 5.9767 | 1.8765 | -4.1003
7.8 | 5.8778 | 1.6957 | -4.1821
7.85 | 5.7788 | 1.5178 | -4.261
7.9 | 5.6798 | 1.3427 | -4.3371
7.95 | 5.5809 | 1.1705 | -4.4104
8 | 5.4819 | 1.0012 | -4.4807
8.05 | 5.3829 | 0.83467 | -4.5482
8.1 | 5.2839 | 0.67105 | -4.6129
8.15 | 5.185 | 0.51029 | -4.6747
8.2 | 5.086 | 0.35238 | -4.7336
8.25 | 4.987 | 0.19734 | -4.7897
8.3 | 4.8881 | 0.045157 | -4.8429
8.35 | 4.7891 | 0.10417 | -4.6849
8.4 | 4.6901 | 0.25063 | -4.4395
8.45 | 4.5911 | 0.39424 | -4.1969
8.5 | 4.4922 | 0.53498 | -3.9572
8.55 | 4.3932 | 0.67286 | -3.7203
8.6 | 4.2942 | 0.80789 | -3.4863
8.65 | 4.1953 | 0.94005 | -3.2552
8.7 | 4.0963 | 1.0694 | -3.0269
8.75 | 3.9973 | 1.1958 | -2.8015
8.8 | 3.8984 | 1.3194 | -2.579
8.85 | 3.7994 | 1.4401 | -2.3593
8.9 | 3.7004 | 1.558 | -2.1424
8.95 | 3.6014 | 1.673 | -1.9285
9 | 3.5025 | 1.7851 | -1.7173
9.05 | 3.4035 | 1.8944 | -1.5091
9.1 | 3.3045 | 2.0008 | -1.3037
9.15 | 3.2056 | 2.1044 | -1.1011
9.2 | 3.1066 | 2.2051 | -0.90147
9.25 | 3.0076 | 2.303 | -0.70466
9.3 | 2.9086 | 2.3979 | -0.5107
9.35 | 2.8097 | 2.4901 | -0.3196
9.4 | 2.7107 | 2.5793 | -0.13136
9.45 | 2.6117 | 2.6657 | 0.054013
9.5 | 2.5128 | 2.7493 | 0.23653
9.55 | 2.4138 | 2.83 | 0.41619
9.6 | 2.3148 | 2.9078 | 0.59299
9.65 | 2.2158 | 2.9828 | 0.76692
9.7 | 2.1169 | 3.0549 | 0.938
9.75 | 2.0179 | 3.1241 | 1.1062
9.8 | 1.9189 | 3.1905 | 1.2716
9.85 | 1.82 | 3.254 | 1.4341
9.9 | 1.721 | 3.3147 | 1.5937
9.95 | 1.622 | 3.3725 | 1.7505
10 | 1.523 | 3.4275 | 1.9044
10.05 | 1.4241 | 3.4795 | 2.0555
10.1 | 1.3251 | 3.5288 | 2.2037
10.15 | 1.2261 | 3.5751 | 2.349
10.2 | 1.1272 | 3.6186 | 2.4915
10.25 | 1.0282 | 3.6593 | 2.6311
10.3 | 0.92922 | 3.6971 | 2.7679
10.35 | 0.83025 | 3.732 | 2.9018
10.4 | 0.73128 | 3.7641 | 3.0328
10.45 | 0.63231 | 3.7933 | 3.161
10.5 | 0.53334 | 3.8196 | 3.2863
10.55 | 0.43437 | 3.8431 | 3.4088
10.6 | 0.33539 | 3.8638 | 3.5284
10.65 | 0.23642 | 3.8815 | 3.6451
10.7 | 0.13745 | 3.8964 | 3.759
10.75 | 0.038481 | 3.9085 | 3.87
10.8 | 0.06049 | 3.9177 | 3.8572
10.85 | 0.15946 | 3.924 | 3.7645
10.9 | 0.25843 | 3.9275 | 3.669
10.95 | 0.3574 | 3.9281 | 3.5707
11 | 0.45637 | 3.9258 | 3.4695
11.05 | 0.55535 | 3.9207 | 3.3654
11.1 | 0.65432 | 3.9128 | 3.2584
11.15 | 0.75329 | 3.9019 | 3.1486
11.2 | 0.85226 | 3.8882 | 3.036
11.25 | 0.95123 | 3.8717 | 2.9205
11.3 | 1.0502 | 3.8523 | 2.8021
11.35 | 1.1492 | 3.83 | 2.6808
11.4 | 1.2481 | 3.8049 | 2.5567
11.45 | 1.3471 | 3.7769 | 2.4298
11.5 | 1.4461 | 3.746 | 2.3
11.55 | 1.5451 | 3.7123 | 2.1673
11.6 | 1.644 | 3.6758 | 2.0317
11.65 | 1.743 | 3.6363 | 1.8933
11.7 | 1.842 | 3.594 | 1.7521
11.75 | 1.9409 | 3.5489 | 1.608
11.8 | 2.0399 | 3.5009 | 1.461
11.85 | 2.1389 | 3.45 | 1.3111
11.9 | 2.2379 | 3.3963 | 1.1584
11.95 | 2.3368 | 3.3397 | 1.0029
12 | 2.4358 | 3.2802 | 0.84445
12.05 | 2.5348 | 3.2179 | 0.68318
12.1 | 2.6337 | 3.1528 | 0.51904
12.15 | 2.7327 | 3.0847 | 0.35204
12.2 | 2.8317 | 3.0139 | 0.18218
12.25 | 2.9307 | 2.9401 | 0.009461
12.3 | 3.0296 | 2.8635 | -0.16612
12.35 | 3.1286 | 2.784 | -0.34456
12.4 | 3.2276 | 2.7017 | -0.52585
12.45 | 3.3265 | 2.6165 | -0.71001
12.5 | 3.4255 | 2.5285 | -0.89703
12.55 | 3.5245 | 2.4376 | -1.0869
12.6 | 3.6234 | 2.3438 | -1.2796
12.65 | 3.7224 | 2.2472 | -1.4752
12.7 | 3.8214 | 2.1477 | -1.6737
12.75 | 3.9204 | 2.0453 | -1.875
12.8 | 4.0193 | 1.9401 | -2.0792
12.85 | 4.1183 | 1.8321 | -2.2862
12.9 | 4.2173 | 1.7211 | -2.4961
12.95 | 4.3162 | 1.6074 | -2.7089
13 | 4.4152 | 1.4907 | -2.9245
13.05 | 4.5142 | 1.3712 | -3.143
13.1 | 4.6132 | 1.2488 | -3.3643
13.15 | 4.7121 | 1.1236 | -3.5885
13.2 | 4.8111 | 0.99553 | -3.8156
13.25 | 4.9101 | 0.86458 | -4.0455
13.3 | 5.009 | 0.73078 | -4.2783
13.35 | 5.108 | 0.59411 | -4.5139
13.4 | 5.207 | 0.45459 | -4.7524
13.45 | 5.306 | 0.3122 | -4.9938
13.5 | 5.4049 | 0.16696 | -5.238
13.55 | 5.5039 | 0.018854 | -5.485
13.6 | 5.6029 | 0.13211 | -5.4708
13.65 | 5.7018 | 0.28593 | -5.4159
13.7 | 5.8008 | 0.44262 | -5.3582
13.75 | 5.8998 | 0.60216 | -5.2976
13.8 | 5.9988 | 0.76457 | -5.2342
13.85 | 6.0977 | 0.92983 | -5.1679
13.9 | 6.1967 | 1.098 | -5.0987
13.95 | 6.2957 | 1.2689 | -5.0267
14 | 6.3946 | 1.4428 | -4.9519
14.05 | 6.4936 | 1.6195 | -4.8741
14.1 | 6.5926 | 1.799 | -4.7935
14.15 | 6.6915 | 1.9815 | -4.7101
14.2 | 6.7905 | 2.1668 | -4.6238
14.25 | 6.8895 | 2.3549 | -4.5346
14.3 | 6.9885 | 2.5459 | -4.4426
14.35 | 7.0874 | 2.7398 | -4.3477
14.4 | 7.1864 | 2.9365 | -4.2499
14.45 | 7.2854 | 3.1361 | -4.1493
14.5 | 7.3843 | 3.3385 | -4.0458
14.55 | 7.4833 | 3.5438 | -3.9395
14.6 | 7.5823 | 3.752 | -3.8303
14.65 | 7.6813 | 3.963 | -3.7183
14.7 | 7.7802 | 4.1769 | -3.6033
14.75 | 7.8792 | 4.3936 | -3.4856
14.8 | 7.9782 | 4.6132 | -3.3649
14.85 | 8.0771 | 4.8357 | -3.2415
14.9 | 8.1761 | 5.061 | -3.1151
14.95 | 8.2751 | 5.2892 | -2.9859
15 | 8.3741 | 5.5202 | -2.8538
Risk Crossover
Risk Crossover

## Normal
[14 empty] | Phi = | 1.618
| ID | Activity | Total Float | Geometric Floats | Critical | Red | Yellow | Green | Criticality Risk | 0.64585 |  | Activity Risk | 0.94373 | Fibonacci Formula | 0.59035
| 1 | Requirements | 0 | 1 | 1 | 0 | 0 | 0
| 2 | Architecture | 0 | 1 | 1 | 0 | 0 | 0 | Critical factor | 4
| 3 | Project Design | 0 | 1 | 1 | 0 | 0 | 0 | Red Factor | 3
| 4 | Test Plan | 65 | 66 | 0 | 0 | 0 | 1 | Yellow Factor | 2
| 5 | Test Harness | 65 | 66 | 0 | 0 | 0 | 1 | Green Factor | 1
| 6 | Logging | 0 | 1 | 1 | 0 | 0 | 0
| 7 | Security | 0 | 1 | 1 | 0 | 0 | 0 | Total | 10
| 8 | Pub/Sub | 15 | 16 | 0 | 0 | 1 | 0
| 9 | Resource A | 25 | 26 | 0 | 0 | 1 | 0 | Critical Limit | 1
| 10 | Resource B | 30 | 31 | 0 | 0 | 0 | 1 | Red Limit | 9
| 11 | Resource Access A | 25 | 26 | 0 | 0 | 1 | 0 | Yellow Limit | 26
| 12 | Resource Access B | 10 | 11 | 0 | 0 | 1 | 0
| 13 | Resource Access C | 0 | 1 | 1 | 0 | 0 | 0
| 14 | EngineA | 5 | 6 | 0 | 1 | 0 | 0
| 15 | EngineB | 0 | 1 | 1 | 0 | 0 | 0
| 16 | EngineC | 30 | 31 | 0 | 0 | 0 | 1
| 17 | ManagerA | 0 | 1 | 1 | 0 | 0 | 0
| 18 | ManagerB | 5 | 6 | 0 | 1 | 0 | 0
| 19 | Client App1 | 5 | 6 | 0 | 1 | 0 | 0
| 20 | Client App2 | 0 | 1 | 1 | 0 | 0 | 0
| 21 | System Testing | 0 | 1 | 1 | 0 | 0 | 0 |  | Sanity Check: | Passed
Total |  |  | 280 |  | 10 | 3 | 4 | 4
21

## Subcritical
[14 empty] | Phi = | 1.618
| ID | Activity | Total Float | Geometric Floats | Critical | Red | Yellow | Green | Criticality Risk | 0.69553 |  | Activity Risk | 0.9653 | Fibonacci Formula | 0.66201
| 1 | Requirements | 0 | 1 | 1 | 0 | 0 | 0
| 2 | Architecture | 0 | 1 | 1 | 0 | 0 | 0 | Critical factor | 4
| 3 | Project Design | 0 | 1 | 1 | 0 | 0 | 0 | Red Factor | 3
| 4 | Test Plan | 0 | 1 | 1 | 0 | 0 | 0 | Yellow Factor | 2
| 5 | Test Harness | 0 | 1 | 1 | 0 | 0 | 0 | Green Factor | 1
| 6 | Logging | 0 | 1 | 1 | 0 | 0 | 0
| 7 | Security | 10 | 11 | 0 | 0 | 1 | 0 | Total | 10
| 8 | Pub/Sub | 0 | 1 | 1 | 0 | 0 | 0
| 9 | Resource A | 0 | 1 | 1 | 0 | 0 | 0 | Critical Limit | 1
| 10 | Resource B | 0 | 1 | 1 | 0 | 0 | 0 | Red Limit | 9
| 11 | Resource Access A | 0 | 1 | 1 | 0 | 0 | 0 | Yellow Limit | 26
| 12 | Resource Access B | 10 | 11 | 0 | 0 | 1 | 0
| 13 | Resource Access C | 10 | 11 | 0 | 0 | 1 | 0
| 14 | EngineA | 0 | 1 | 1 | 0 | 0 | 0
| 15 | EngineB | 60 | 61 | 0 | 0 | 0 | 1
| 16 | EngineC | 60 | 61 | 0 | 0 | 0 | 1
| 17 | ManagerA | 0 | 1 | 1 | 0 | 0 | 0
| 18 | ManagerB | 60 | 61 | 0 | 0 | 0 | 1
| 19 | Client App1 | 60 | 61 | 0 | 0 | 0 | 1
| 20 | Client App2 | 0 | 1 | 1 | 0 | 0 | 0
| 21 | System Testing | 0 | 1 | 1 | 0 | 0 | 0 |  | Sanity Check: | Passed
Total |  |  |  |  | 14 | 0 | 3 | 4
21

## TopDev2
[14 empty] | Phi = | 1.618
| ID | Activity | Total Float | Geometric Floats | Critical | Red | Yellow | Green | Criticality Risk | 0.62139 |  | Activity Risk | 0.93187 | Fibonacci Formula | 0.5639
| 1 | Requirements | 0 | 1 | 1 | 0 | 0 | 0
| 2 | Architecture | 0 | 1 | 1 | 0 | 0 | 0 | Critical factor | 4
| 3 | Project Design | 0 | 1 | 1 | 0 | 0 | 0 | Red Factor | 3
| 4 | Test Plan | 55 | 56 | 0 | 0 | 0 | 1 | Yellow Factor | 2
| 5 | Test Harness | 55 | 56 | 0 | 0 | 0 | 1 | Green Factor | 1
| 6 | Logging | 0 | 1 | 1 | 0 | 0 | 0
| 7 | Security | 0 | 1 | 1 | 0 | 0 | 0 | Total | 10
| 8 | Pub/Sub | 15 | 16 | 0 | 0 | 1 | 0
| 9 | Resource A | 30 | 31 | 0 | 0 | 0 | 1 | Critical Limit | 1
| 10 | Resource B | 25 | 26 | 0 | 0 | 1 | 0 | Red Limit | 9
| 11 | Resource Access A | 30 | 31 | 0 | 0 | 0 | 1 | Yellow Limit | 26
| 12 | Resource Access B | 5 | 6 | 0 | 1 | 0 | 0
| 13 | Resource Access C | 0 | 1 | 1 | 0 | 0 | 0
| 14 | EngineA | 10 | 11 | 0 | 0 | 1 | 0
| 15 | EngineB | 0 | 1 | 1 | 0 | 0 | 0
| 16 | EngineC | 15 | 16 | 0 | 0 | 1 | 0
| 17 | ManagerA | 10 | 11 | 0 | 0 | 1 | 0
| 18 | ManagerB | 0 | 1 | 1 | 0 | 0 | 0
| 19 | Client App1 | 0 | 1 | 1 | 0 | 0 | 0
| 20 | Client App2 | 10 | 11 | 0 | 0 | 1 | 0
| 21 | System Testing | 0 | 1 | 1 | 0 | 0 | 0 |  | Sanity Check: | Passed
Total |  |  | 260 |  | 10 | 1 | 6 | 4
21

## TopDev2+TopDev1
[14 empty] | Phi = | 1.618
| ID | Activity | Total Float | Geometric Floats | Critical | Red | Yellow | Green | Criticality Risk | 0.72292 |  | Activity Risk | 0.94067 | Fibonacci Formula | 0.66201
| 1 | Requirements | 0 | 1 | 1 | 0 | 0 | 0
| 2 | Architecture | 0 | 1 | 1 | 0 | 0 | 0 | Critical factor | 4
| 3 | Project Design | 0 | 1 | 1 | 0 | 0 | 0 | Red Factor | 3
| 4 | Test Plan | 35 | 36 | 0 | 0 | 0 | 1 | Yellow Factor | 2
| 5 | Test Harness | 35 | 36 | 0 | 0 | 0 | 1 | Green Factor | 1
| 6 | Logging | 0 | 1 | 1 | 0 | 0 | 0
| 7 | Security | 0 | 1 | 1 | 0 | 0 | 0 | Total | 10
| 8 | Pub/Sub | 10 | 11 | 0 | 0 | 1 | 0
| 9 | Resource A | 10 | 11 | 0 | 0 | 1 | 0 | Critical Limit | 1
| 10 | Resource B | 10 | 11 | 0 | 0 | 1 | 0 | Red Limit | 9
| 11 | Resource Access A | 10 | 11 | 0 | 0 | 1 | 0 | Yellow Limit | 26
| 12 | Resource Access B | 0 | 1 | 1 | 0 | 0 | 0
| 13 | Resource Access C | 5 | 6 | 0 | 1 | 0 | 0
| 14 | EngineA | 5 | 6 | 0 | 1 | 0 | 0
| 15 | EngineB | 0 | 1 | 1 | 0 | 0 | 0
| 16 | EngineC | 25 | 26 | 0 | 0 | 1 | 0
| 17 | ManagerA | 0 | 1 | 1 | 0 | 0 | 0
| 18 | ManagerB | 0 | 1 | 1 | 0 | 0 | 0
| 19 | Client App1 | 0 | 1 | 1 | 0 | 0 | 0
| 20 | Client App2 | 0 | 1 | 1 | 0 | 0 | 0
| 21 | System Testing | 0 | 1 | 1 | 0 | 0 | 0 |  | Sanity Check: | Passed
Total |  |  | 145 |  | 12 | 2 | 5 | 2
21

## Infra+Clients Front End
[14 empty] | Phi = | 1.618
| ID | Activity | Total Float | Geometric Floats | Critical | Red | Yellow | Green | Criticality Risk | 0.71784 |  | Activity Risk | 0.92796 | Fibonacci Formula | 0.64444
| 1 | Requirements | 0 | 1 | 1 | 0 | 0 | 0
| 2 | Architecture | 0 | 1 | 1 | 0 | 0 | 0 | Critical factor | 4
| 3 | Project Design | 0 | 1 | 1 | 0 | 0 | 0 | Red Factor | 3
| 4 | Test Plan | 20 | 21 | 0 | 0 | 1 | 0 | Yellow Factor | 2
| 5 | Test Harness | 20 | 21 | 0 | 0 | 1 | 0 | Green Factor | 1
| 6 | Logging | 0 | 1 | 1 | 0 | 0 | 0
| 7 | Security | 0 | 1 | 1 | 0 | 0 | 0 | Total | 10
| 8 | Pub/Sub | 10 | 11 | 0 | 0 | 1 | 0
| 9 | Resource A | 0 | 1 | 1 | 0 | 0 | 0 | Critical Limit | 5
| 10 | Resource B | 10 | 11 | 0 | 0 | 1 | 0 | Red Limit | 9
| 11 | Resource Access A | 0 | 1 | 1 | 0 | 0 | 0 | Yellow Limit | 26
| 12 | Resource Access B | 10 | 11 | 0 | 0 | 1 | 0
| 13 | Resource Access C | 20 | 21 | 0 | 0 | 1 | 0
| 14 | EngineA | 15 | 16 | 0 | 0 | 1 | 0
| 15 | EngineB | 10 | 11 | 0 | 0 | 1 | 0
| 16 | EngineC | 40 | 41 | 0 | 0 | 0 | 1
| 17 | ManagerA | 0 | 1 | 1 | 0 | 0 | 0
| 18 | ManagerB | 10 | 11 | 0 | 0 | 1 | 0
| 19 | Client App1 | 5 | 6 | 1 | 0 | 0 | 0
| 20 | Client App2 | 0 | 1 | 1 | 0 | 0 | 0
| 21 | System Testing | 0 | 1 | 1 | 0 | 0 | 0
| 22 | Client App1 Design | 5 | 6 | 1 | 0 | 0 | 0
| 23 | Client App2 Design | 0 | 1 | 1 | 0 | 0 | 0 |  | Sanity Check: | Passed
|  |  | 175 |  | 13 | 0 | 9 | 1
Total
23

## Simulators
[14 empty] | Phi = | 1.618
| ID | Activity | Total Float | Geometric Floats | Critical | Red | Yellow | Green | Criticality Risk | 0.71624 |  | Activity Risk | 0.91269 | Fibonacci Formula | 0.68779
| 1 | Requirements | 0 | 1 | 1 | 0 | 0 | 0
| 2 | Architecture | 0 | 1 | 1 | 0 | 0 | 0 | Critical factor | 4
| 3 | Project Design | 0 | 1 | 1 | 0 | 0 | 0 | Red Factor | 3
| 4 | Test Plan | 5 | 6 | 1 | 0 | 0 | 0 | Yellow Factor | 2
| 5 | Test Harness | 5 | 6 | 1 | 0 | 0 | 0 | Green Factor | 1
| 6 | Logging | 0 | 1 | 1 | 0 | 0 | 0
| 7 | Security | 0 | 1 | 1 | 0 | 0 | 0 | Total | 10
| 8 | Pub/Sub | 10 | 11 | 0 | 0 | 1 | 0
| 9 | Resource A | 0 | 1 | 1 | 0 | 0 | 0 | Critical Limit | 5
| 10 | Resource B | 5 | 6 | 1 | 0 | 0 | 0 | Red Limit | 9
| 11 | Resource Access A | 0 | 1 | 1 | 0 | 0 | 0 | Yellow Limit | 26
| 12 | Resource Access B | 5 | 6 | 1 | 0 | 0 | 0
| 13 | Resource Access C | 15 | 16 | 0 | 0 | 1 | 0
| 14 | EngineA | 15 | 16 | 0 | 0 | 1 | 0
| 15 | EngineB | 5 | 6 | 1 | 0 | 0 | 0
| 16 | EngineC | 35 | 36 | 0 | 0 | 0 | 1
| 17 | ManagerA | 0 | 1 | 1 | 0 | 0 | 0
| 18 | ManagerB | 5 | 6 | 1 | 0 | 0 | 0
| 19 | Client App1 | 0 | 1 | 1 | 0 | 0 | 0
| 20 | Client App2 | 0 | 1 | 1 | 0 | 0 | 0
| 21 | System Testing | 0 | 1 | 1 | 0 | 0 | 0
| 22 | Client App1 Design | 5 | 6 | 1 | 0 | 0 | 0
| 23 | Client App2 Design | 0 | 1 | 1 | 0 | 0 | 0
| 24 | ManagerA Simulator | 30 | 31 | 0 | 0 | 0 | 1
| 25 | ManagerB Simulator | 30 | 31 | 0 | 0 | 0 | 1
| 26 | Client App1 | 30 | 31 | 0 | 0 | 0 | 1
| 27 | Client App2 | 30 | 31 | 0 | 0 | 0 | 1 |  | Sanity Check: | Passed
|  |  | 230 |  | 19 | 0 | 3 | 5
Total
27