## D1
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.28571 | Activity Risk | 0.26701 | Fibonacci Formula | 0.27245
1 | Requirements | 75 |  | 75 | 0 | 0 | 0 | 1
2 | Architecture | 75 |  | 75 | 0 | 0 | 0 | 1 | Critical factor | 4
3 | Project Design | 75 |  | 75 | 0 | 0 | 0 | 1 | Red Factor | 3
4 | Test Plan | 140 | 112 | 112 | 0 | 0 | 0 | 1 | Yellow Factor | 2
5 | Test Harness | 140 | 112 | 112 | 0 | 0 | 0 | 1 | Green Factor | 1
6 | Logging | 75 |  | 75 | 0 | 0 | 0 | 1
7 | Security | 75 |  | 75 | 0 | 0 | 0 | 1 | Total | 10
8 | Pub/Sub | 90 |  | 90 | 0 | 0 | 0 | 1
9 | Resource A | 100 |  | 100 | 0 | 0 | 0 | 1
10 | Resource B | 105 |  | 105 | 0 | 0 | 0 | 1 | Red Limit | 9
11 | Resource Access A | 100 |  | 100 | 0 | 0 | 0 | 1 | Yellow Limit | 26
12 | Resource Access B | 85 |  | 85 | 0 | 0 | 0 | 1
13 | Resource Access C | 75 |  | 75 | 0 | 0 | 0 | 1
14 | EngineA | 80 |  | 80 | 0 | 0 | 0 | 1
15 | EngineB | 75 |  | 75 | 0 | 0 | 0 | 1
16 | EngineC | 105 |  | 105 | 0 | 0 | 0 | 1 | Sanity Check: | Passed
17 | ManagerA | 75 |  | 75 | 0 | 0 | 0 | 1
18 | ManagerB | 80 |  | 80 | 0 | 0 | 0 | 1
19 | Client App1 | 80 |  | 80 | 0 | 0 | 0 | 1
20 | Client App2 | 75 |  | 75 | 0 | 0 | 0 | 1
21 | System Testing | 0 |  | 0 | 1 | 0 | 0 | 0 | Decompressed start date for System Testing: |  | 2014-01-27

## D2
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.28571 | Activity Risk | 0.3261 | Fibonacci Formula | 0.27245
1 | Requirements | 45 |  | 45 | 0 | 0 | 0 | 1
2 | Architecture | 45 |  | 45 | 0 | 0 | 0 | 1 | Critical factor | 4
3 | Project Design | 45 |  | 45 | 0 | 0 | 0 | 1 | Red Factor | 3
4 | Test Plan | 110 | 79 | 79 | 0 | 0 | 0 | 1 | Yellow Factor | 2
5 | Test Harness | 110 | 79 | 79 | 0 | 0 | 0 | 1 | Green Factor | 1
6 | Logging | 45 |  | 45 | 0 | 0 | 0 | 1
7 | Security | 45 |  | 45 | 0 | 0 | 0 | 1 | Total | 10
8 | Pub/Sub | 60 |  | 60 | 0 | 0 | 0 | 1
9 | Resource A | 70 |  | 70 | 0 | 0 | 0 | 1
10 | Resource B | 75 |  | 75 | 0 | 0 | 0 | 1 | Red Limit | 9
11 | Resource Access A | 70 |  | 70 | 0 | 0 | 0 | 1 | Yellow Limit | 26
12 | Resource Access B | 55 |  | 55 | 0 | 0 | 0 | 1
13 | Resource Access C | 45 |  | 45 | 0 | 0 | 0 | 1
14 | EngineA | 50 |  | 50 | 0 | 0 | 0 | 1
15 | EngineB | 45 |  | 45 | 0 | 0 | 0 | 1
16 | EngineC | 75 |  | 75 | 0 | 0 | 0 | 1 | Sanity Check: | Passed
17 | ManagerA | 45 |  | 45 | 0 | 0 | 0 | 1
18 | ManagerB | 50 |  | 50 | 0 | 0 | 0 | 1
19 | Client App1 | 50 |  | 50 | 0 | 0 | 0 | 1
20 | Client App2 | 45 |  | 45 | 0 | 0 | 0 | 1
21 | System Testing | 0 |  | 0 | 1 | 0 | 0 | 0 | Decompressed start date for System Testing: |  | 2013-12-16

## D3
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.42857 | Activity Risk | 0.44654 | Fibonacci Formula | 0.35582
1 | Requirements | 20 |  | 20 | 0 | 0 | 1 | 0
2 | Architecture | 20 |  | 20 | 0 | 0 | 1 | 0 | Critical factor | 4
3 | Project Design | 20 |  | 20 | 0 | 0 | 1 | 0 | Red Factor | 3
4 | Test Plan | 85 | 53 | 53 | 0 | 0 | 0 | 1 | Yellow Factor | 2
5 | Test Harness | 85 | 53 | 53 | 0 | 0 | 0 | 1 | Green Factor | 1
6 | Logging | 20 |  | 20 | 0 | 0 | 1 | 0
7 | Security | 20 |  | 20 | 0 | 0 | 1 | 0 | Total | 10
8 | Pub/Sub | 35 |  | 35 | 0 | 0 | 0 | 1
9 | Resource A | 45 |  | 45 | 0 | 0 | 0 | 1
10 | Resource B | 50 |  | 50 | 0 | 0 | 0 | 1 | Red Limit | 9
11 | Resource Access A | 45 |  | 45 | 0 | 0 | 0 | 1 | Yellow Limit | 26
12 | Resource Access B | 30 |  | 30 | 0 | 0 | 0 | 1
13 | Resource Access C | 20 |  | 20 | 0 | 0 | 1 | 0
14 | EngineA | 25 |  | 25 | 0 | 0 | 1 | 0
15 | EngineB | 20 |  | 20 | 0 | 0 | 1 | 0
16 | EngineC | 50 |  | 50 | 0 | 0 | 0 | 1 | Sanity Check: | Passed
17 | ManagerA | 20 |  | 20 | 0 | 0 | 1 | 0
18 | ManagerB | 25 |  | 25 | 0 | 0 | 1 | 0
19 | Client App1 | 25 |  | 25 | 0 | 0 | 1 | 0
20 | Client App2 | 20 |  | 20 | 0 | 0 | 1 | 0
21 | System Testing | 0 |  | 0 | 1 | 0 | 0 | 0 | Decompressed start date for System Testing: |  | 2013-11-11
0
0
0
0

## D4
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.45238 | Activity Risk | 0.53931 | Fibonacci Formula | 0.36971
1 | Requirements | 10 |  | 10 | 0 | 0 | 1 | 0
2 | Architecture | 10 |  | 10 | 0 | 0 | 1 | 0 | Critical factor | 4
3 | Project Design | 10 |  | 10 | 0 | 0 | 1 | 0 | Red Factor | 3
4 | Test Plan | 75 | 43 | 43 | 0 | 0 | 0 | 1 | Yellow Factor | 2
5 | Test Harness | 75 | 43 | 43 | 0 | 0 | 0 | 1 | Green Factor | 1
6 | Logging | 10 |  | 10 | 0 | 0 | 1 | 0
7 | Security | 10 |  | 10 | 0 | 0 | 1 | 0 | Total | 10
8 | Pub/Sub | 25 |  | 25 | 0 | 0 | 1 | 0
9 | Resource A | 35 |  | 35 | 0 | 0 | 0 | 1
10 | Resource B | 40 |  | 40 | 0 | 0 | 0 | 1 | Red Limit | 9
11 | Resource Access A | 35 |  | 35 | 0 | 0 | 0 | 1 | Yellow Limit | 26
12 | Resource Access B | 20 |  | 20 | 0 | 0 | 1 | 0
13 | Resource Access C | 10 |  | 10 | 0 | 0 | 1 | 0
14 | EngineA | 15 |  | 15 | 0 | 0 | 1 | 0
15 | EngineB | 10 |  | 10 | 0 | 0 | 1 | 0
16 | EngineC | 40 |  | 40 | 0 | 0 | 0 | 1 | Sanity Check: | Passed
17 | ManagerA | 10 |  | 10 | 0 | 0 | 1 | 0
18 | ManagerB | 15 |  | 15 | 0 | 0 | 1 | 0
19 | Client App1 | 15 |  | 15 | 0 | 0 | 1 | 0
20 | Client App2 | 10 |  | 10 | 0 | 0 | 1 | 0
21 | System Testing | 0 |  | 0 | 1 | 0 | 0 | 0 | Decompressed start date for System Testing: |  | 2013-10-28