## Time-Cost Curve
Design Option | Duration | Total Cost | Direct Cost | Indirect Cost
Simulators | 7.1333 | 63.54 | 34.8067 | 28.7333
Infra + Clients Front End | 7.8333 | 62.6067 | 30.3733 | 32.2333
TopDev2+TopDev1 | 8.5333 | 59.2933 | 26.5933 | 32.7
TopDev2 | 9.4667 | 61.1133 | 24.2133 | 36.9
Normal | 9.9333 | 61.0667 | 21.8333 | 39.2333
Sub-Critical | 13.4333 | 77.6333 | 20.9 | 56.7333
Simulators
Infra+Clients
Front-End
TopDev2+
TopDev1
TopDev2
Normal
Subcritical

## Time-Cost Curve trends
Design Option | Duration | Total Cost | Direct Cost | Indirect Cost
Simulators | 7.1333 | 63.54 | 34.8067 | 28.7333
Infra + Clients Front End | 7.8333 | 62.6067 | 30.3733 | 32.2333
TopDev2+TopDev1 | 8.5333 | 59.2933 | 26.5933 | 32.7
TopDev2 | 9.4667 | 61.1133 | 24.2133 | 36.9
Normal | 9.9333 | 61.0667 | 21.8333 | 39.2333
Sub-Critical | 13.4333 | 77.6333 | 20.9 | 56.7333
[5 empty] | Direct | 0.65278567x2 - 15.59707873x + 112.63972962
[5 empty] | Indirect | 4.44825073x - 4.00857629
[5 empty] | Total | 0.90148285x2 - 16.32274439x + 134.25345358

## Model
Coefficients |  | Direct Cost | Indirect cost | Total Cost
a |  | 0.65279 | 4.4483 | 0.65279
b |  | -15.5971 | -4.0086 | -11.1488
c |  | 112.6397 |  | 108.6312
Duration | Total Cost | Direct Cost | Indirect Cost
6 | 65.2385 | 42.5575 | 22.6809
6.1 | 64.9135 | 41.7877 | 23.1258
6.2 | 64.6015 | 41.0309 | 23.5706
6.3 | 64.3026 | 40.2872 | 24.0154
6.4 | 64.0168 | 39.5565 | 24.4602
6.5 | 63.744 | 38.8389 | 24.9051
6.6 | 63.4842 | 38.1344 | 25.3499
6.7 | 63.2376 | 37.4429 | 25.7947
6.8 | 63.0039 | 36.7644 | 26.2395
6.9 | 62.7834 | 36.099 | 26.6844
7 | 62.5759 | 35.4467 | 27.1292
7.1 | 62.3814 | 34.8074 | 27.574
7.2 | 62.2 | 34.1812 | 28.0188
7.3 | 62.0317 | 33.568 | 28.4637
7.4 | 61.8764 | 32.9679 | 28.9085
7.5 | 61.7341 | 32.3808 | 29.3533
7.6 | 61.605 | 31.8068 | 29.7981
7.7 | 61.4888 | 31.2459 | 30.243
7.8 | 61.3858 | 30.698 | 30.6878
7.9 | 61.2958 | 30.1632 | 31.1326
8 | 61.2188 | 29.6414 | 31.5774
8.1 | 61.1549 | 29.1327 | 32.0223
8.2 | 61.1041 | 28.637 | 32.4671
8.3 | 61.0663 | 28.1544 | 32.9119
8.4 | 61.0416 | 27.6848 | 33.3567
8.5 | 61.0299 | 27.2283 | 33.8016
8.6 | 61.0313 | 26.7849 | 34.2464
8.7 | 61.0457 | 26.3545 | 34.6912
8.8 | 61.0732 | 25.9372 | 35.136
8.9 | 61.1137 | 25.5329 | 35.5809
9 | 61.1673 | 25.1417 | 36.0257
9.1 | 61.234 | 24.7635 | 36.4705 |  | Normal | 9.9333 | 80
9.2 | 61.3137 | 24.3984 | 36.9153 |  | Min Total Cost | 8.5394 | 80
9.3 | 61.4065 | 24.0463 | 37.3602
9.4 | 61.5123 | 23.7073 | 37.805
9.5 | 61.6312 | 23.3814 | 38.2498
9.6 | 61.7631 | 23.0685 | 38.6946
9.7 | 61.9081 | 22.7687 | 39.1395
9.8 | 62.0662 | 22.4819 | 39.5843
9.9 | 62.2373 | 22.2082 | 40.0291
10 | 62.4214 | 21.9475 | 40.4739
10.1 | 62.6187 | 21.6999 | 40.9188
10.2 | 62.8289 | 21.4653 | 41.3636
10.3 | 63.0523 | 21.2439 | 41.8084
10.4 | 63.2886 | 21.0354 | 42.2532
10.5 | 63.5381 | 20.84 | 42.6981
10.6 | 63.8006 | 20.6577 | 43.1429
10.7 | 64.0761 | 20.4884 | 43.5877
10.8 | 64.3647 | 20.3322 | 44.0325
10.9 | 64.6664 | 20.189 | 44.4774
11 | 64.9811 | 20.0589 | 44.9222
11.1 | 65.3089 | 19.9419 | 45.367
11.2 | 65.6497 | 19.8379 | 45.8118
11.3 | 66.0036 | 19.7469 | 46.2567
11.4 | 66.3705 | 19.6691 | 46.7015
11.5 | 66.7505 | 19.6042 | 47.1463
11.6 | 67.1436 | 19.5525 | 47.5911
11.7 | 67.5497 | 19.5137 | 48.036
11.8 | 67.9689 | 19.4881 | 48.4808
11.9 | 68.4011 | 19.4755 | 48.9256
12 | 68.8464 | 19.4759 | 49.3704
12.1 | 69.3047 | 19.4894 | 49.8153
12.2 | 69.7761 | 19.516 | 50.2601
12.3 | 70.2605 | 19.5556 | 50.7049
12.4 | 70.758 | 19.6083 | 51.1497
12.5 | 71.2686 | 19.674 | 51.5946
12.6 | 71.7922 | 19.7528 | 52.0394
12.7 | 72.3288 | 19.8446 | 52.4842
12.8 | 72.8786 | 19.9495 | 52.929
12.9 | 73.4413 | 20.0675 | 53.3739
13 | 74.0172 | 20.1985 | 53.8187
13.1 | 74.6061 | 20.3425 | 54.2635
13.2 | 75.208 | 20.4997 | 54.7083
13.3 | 75.823 | 20.6698 | 55.1532
13.4 | 76.4511 | 20.8531 | 55.598
13.5 | 77.0922 | 21.0494 | 56.0428
13.6 | 77.7463 | 21.2587 | 56.4876
13.7 | 78.4136 | 21.4811 | 56.9325
13.8 | 79.0938 | 21.7165 | 57.3773
13.9 | 79.7872 | 21.9651 | 57.8221
14 | 80.4936 | 22.2266 | 58.2669
14.1 | 81.213 | 22.5012 | 58.7118
14.2 | 81.9455 | 22.7889 | 59.1566
14.3 | 82.6911 | 23.0896 | 59.6014
14.4 | 83.4497 | 23.4034 | 60.0462
14.5 | 84.2213 | 23.7303 | 60.4911
14.6 | 85.0061 | 24.0702 | 60.9359
14.7 | 85.8038 | 24.4231 | 61.3807
14.8 | 86.6147 | 24.7891 | 61.8255
14.9 | 87.4386 | 25.1682 | 62.2704
15 | 88.2755 | 25.5603 | 62.7152

## Death Zone
Coefficients |  | Direct Cost | Indirect cost | Total Cost
a |  | 0.65279 | 4.4483 | 0.65279
b |  | -15.5971 | -4.0086 | -11.1488
c |  | 112.6397 |  | 108.6312
Duration | Total Cost | Direct Cost | Indirect Cost | Average Staffing
6 | 65.2385 | 42.5575 | 22.6809 | 10.8731
6.1 | 64.9135 | 41.7877 | 23.1258 | 10.6416
6.2 | 64.6015 | 41.0309 | 23.5706 | 10.4196
6.3 | 64.3026 | 40.2872 | 24.0154 | 10.2068
6.4 | 64.0168 | 39.5565 | 24.4602 | 10.0026
6.5 | 63.744 | 38.8389 | 24.9051 | 9.8068
6.6 | 63.4842 | 38.1344 | 25.3499 | 9.6188
6.7 | 63.2376 | 37.4429 | 25.7947 | 9.4384
6.8 | 63.0039 | 36.7644 | 26.2395 | 9.2653
6.9 | 62.7834 | 36.099 | 26.6844 | 9.099
7 | 62.5759 | 35.4467 | 27.1292 | 8.9394
7.1 | 62.3814 | 34.8074 | 27.574 | 8.7861
7.2 | 62.2 | 34.1812 | 28.0188 | 8.6389
7.3 | 62.0317 | 33.568 | 28.4637 | 8.4975
7.4 | 61.8764 | 32.9679 | 28.9085 | 8.3617
7.5 | 61.7341 | 32.3808 | 29.3533 | 8.2312
7.6 | 61.605 | 31.8068 | 29.7981 | 8.1059
7.7 | 61.4888 | 31.2459 | 30.243 | 7.9856
7.8 | 61.3858 | 30.698 | 30.6878 | 7.87
7.9 | 61.2958 | 30.1632 | 31.1326 | 7.759
8 | 61.2188 | 29.6414 | 31.5774 | 7.6524
8.1 | 61.1549 | 29.1327 | 32.0223 | 7.55
8.2 | 61.1041 | 28.637 | 32.4671 | 7.4517
8.3 | 61.0663 | 28.1544 | 32.9119 | 7.3574
8.4 | 61.0416 | 27.6848 | 33.3567 | 7.2669
8.5 | 61.0299 | 27.2283 | 33.8016 | 7.18
8.6 | 61.0313 | 26.7849 | 34.2464 | 7.0967
8.7 | 61.0457 | 26.3545 | 34.6912 | 7.0167
8.8 | 61.0732 | 25.9372 | 35.136 | 6.9401
8.9 | 61.1137 | 25.5329 | 35.5809 | 6.8667
9 | 61.1673 | 25.1417 | 36.0257 | 6.7964
9.1 | 61.234 | 24.7635 | 36.4705 | 6.729
9.2 | 61.3137 | 24.3984 | 36.9153 | 6.6645
9.3 | 61.4065 | 24.0463 | 37.3602 | 6.6028
9.4 | 61.5123 | 23.7073 | 37.805 | 6.5439
9.5 | 61.6312 | 23.3814 | 38.2498 | 6.4875
9.6 | 61.7631 | 23.0685 | 38.6946 | 6.4337
9.7 | 61.9081 | 22.7687 | 39.1395 | 6.3823
9.8 | 62.0662 | 22.4819 | 39.5843 | 6.3333
9.9 | 62.2373 | 22.2082 | 40.0291 | 6.2866
10 | 62.4214 | 21.9475 | 40.4739 | 6.2421
10.1 | 62.6187 | 21.6999 | 40.9188 | 6.1999
10.2 | 62.8289 | 21.4653 | 41.3636 | 6.1597
10.3 | 63.0523 | 21.2439 | 41.8084 | 6.1216
10.4 | 63.2886 | 21.0354 | 42.2532 | 6.0854
10.5 | 63.5381 | 20.84 | 42.6981 | 6.0512
10.6 | 63.8006 | 20.6577 | 43.1429 | 6.0189
10.7 | 64.0761 | 20.4884 | 43.5877 | 5.9884
10.8 | 64.3647 | 20.3322 | 44.0325 | 5.9597
10.9 | 64.6664 | 20.189 | 44.4774 | 5.9327
11 | 64.9811 | 20.0589 | 44.9222 | 5.9074
11.1 | 65.3089 | 19.9419 | 45.367 | 5.8837
11.2 | 65.6497 | 19.8379 | 45.8118 | 5.8616
11.3 | 66.0036 | 19.7469 | 46.2567 | 5.841
11.4 | 66.3705 | 19.6691 | 46.7015 | 5.822
11.5 | 66.7505 | 19.6042 | 47.1463 | 5.8044
11.6 | 67.1436 | 19.5525 | 47.5911 | 5.7882
11.7 | 67.5497 | 19.5137 | 48.036 | 5.7735
11.8 | 67.9689 | 19.4881 | 48.4808 | 5.7601
11.9 | 68.4011 | 19.4755 | 48.9256 | 5.748
12 | 68.8464 | 19.4759 | 49.3704 | 5.7372
12.1 | 69.3047 | 19.4894 | 49.8153 | 5.7277
12.2 | 69.7761 | 19.516 | 50.2601 | 5.7194
12.3 | 70.2605 | 19.5556 | 50.7049 | 5.7122
12.4 | 70.758 | 19.6083 | 51.1497 | 5.7063
12.5 | 71.2686 | 19.674 | 51.5946 | 5.7015
12.6 | 71.7922 | 19.7528 | 52.0394 | 5.6978
12.7 | 72.3288 | 19.8446 | 52.4842 | 5.6952
12.8 | 72.8786 | 19.9495 | 52.929 | 5.6936
12.9 | 73.4413 | 20.0675 | 53.3739 | 5.6931
13 | 74.0172 | 20.1985 | 53.8187 | 5.6936
13.1 | 74.6061 | 20.3425 | 54.2635 | 5.6951
13.2 | 75.208 | 20.4997 | 54.7083 | 5.6976
13.3 | 75.823 | 20.6698 | 55.1532 | 5.701
13.4 | 76.4511 | 20.8531 | 55.598 | 5.7053
13.5 | 77.0922 | 21.0494 | 56.0428 | 5.7105
13.6 | 77.7463 | 21.2587 | 56.4876 | 5.7166
13.7 | 78.4136 | 21.4811 | 56.9325 | 5.7236
13.8 | 79.0938 | 21.7165 | 57.3773 | 5.7314
13.9 | 79.7872 | 21.9651 | 57.8221 | 5.7401
14 | 80.4936 | 22.2266 | 58.2669 | 5.7495
14.1 | 81.213 | 22.5012 | 58.7118 | 5.7598
14.2 | 81.9455 | 22.7889 | 59.1566 | 5.7708
14.3 | 82.6911 | 23.0896 | 59.6014 | 5.7826
14.4 | 83.4497 | 23.4034 | 60.0462 | 5.7951
14.5 | 84.2213 | 23.7303 | 60.4911 | 5.8084
14.6 | 85.0061 | 24.0702 | 60.9359 | 5.8223
14.7 | 85.8038 | 24.4231 | 61.3807 | 5.837
14.8 | 86.6147 | 24.7891 | 61.8255 | 5.8523
14.9 | 87.4386 | 25.1682 | 62.2704 | 5.8684
15 | 88.2755 | 25.5603 | 62.7152 | 5.885
15.1 | 89.1255 | 25.9655 | 63.16 | 5.9024
15.2 | 89.9886 | 26.3837 | 63.6048 | 5.9203
15.3 | 90.8647 | 26.815 | 64.0497 | 5.9389
15.4 | 91.7539 | 27.2594 | 64.4945 | 5.958
15.5 | 92.6561 | 27.7168 | 64.9393 | 5.9778
15.6 | 93.5714 | 28.1872 | 65.3841 | 5.9982
15.7 | 94.4997 | 28.6707 | 65.829 | 6.0191
15.8 | 95.4411 | 29.1673 | 66.2738 | 6.0406
15.9 | 96.3955 | 29.6769 | 66.7186 | 6.0626
16 | 97.363 | 30.1996 | 67.1634 | 6.0852
16.1 | 98.3436 | 30.7353 | 67.6083 | 6.1083
16.2 | 99.3372 | 31.2841 | 68.0531 | 6.1319

## Project Plans
Subcritical |  | Normal |  | TopDev2 |  | TopDev2+TopDev1 |  | Infra+Clients Front End |  | Simulators |  | No Test engineer |  | Sub Critical
Planned Completion Date | Planned Earned Value | Planned Completion Date | Planned Earned Value | Planned Completion Date | Planned Earned Value | Planned Completion Date | Planned Earned Value | Planned Completion Date | Planned Earned Value | Planned Completion Date | Planned Earned Value | Planned Completion Date | Planned Earned Value | Planned Completion Date | Planned Earned Value
2013-01-28 | 0% | 2013-01-28 | 0% | 2013-01-28 | 0% | 2013-01-28 | 0% | 2013-01-28 | 0% | 2013-01-28 | 0% | 2013-01-28 | 0% | 2013-01-28 | 0%
2013-02-15 | 3.571% | 2013-02-15 | 3.589% | 2013-02-15 | 3.797% | 2013-02-15 | 4.11% | 2013-02-15 | 3.947% | 2013-02-15 | 3.513% | 2013-02-15 | 3.589% | 2013-02-15 | 3.589%
2013-03-15 | 8.333% | 2013-03-15 | 8.373% | 2013-03-15 | 8.861% | 2013-03-15 | 9.589% | 2013-03-01 | 6.579% | 2013-03-01 | 5.855% | 2013-03-15 | 8.373% | 2013-03-15 | 8.373%
2013-04-12 | 13.1% | 2013-04-12 | 13.16% | 2013-04-12 | 13.92% | 2013-04-12 | 15.07% | 2013-03-08 | 7.895% | 2013-03-08 | 7.026% | 2013-04-12 | 13.16% | 2013-04-12 | 13.16%
2013-04-12 | 13.1% | 2013-04-12 | 13.16% | 2013-04-12 | 13.92% | 2013-04-12 | 15.07% | 2013-03-15 | 13.16% | 2013-03-15 | 11.71% | 2013-04-12 | 13.16% | 2013-04-12 | 13.16%
2013-05-03 | 16.67% | 2013-05-03 | 16.75% | 2013-05-03 | 17.72% | 2013-04-26 | 17.81% | 2013-03-22 | 17.11% | 2013-03-22 | 15.22% | 2013-05-03 | 16.75% | 2013-05-03 | 16.75%
2013-05-10 | 17.86% | 2013-05-03 | 20.33% | 2013-05-03 | 21.52% | 2013-05-03 | 19.18% | 2013-03-22 | 17.11% | 2013-03-22 | 15.22% | 2013-05-03 | 20.33% | 2013-05-10 | 17.94%
2013-05-31 | 22.62% | 2013-05-10 | 21.53% | 2013-05-10 | 22.78% | 2013-05-03 | 23.29% | 2013-04-05 | 20.26% | 2013-04-05 | 18.03% | 2013-05-10 | 21.53% | 2013-05-31 | 22.73%
2013-05-31 | 26.19% | 2013-05-24 | 28.71% | 2013-05-24 | 30.38% | 2013-05-17 | 27.4% | 2013-04-12 | 25.53% | 2013-04-12 | 22.72% | 2013-05-31 | 26.32% | 2013-05-31 | 26.32%
2013-05-31 | 26.19% | 2013-05-31 | 33.49% | 2013-05-31 | 35.44% | 2013-05-17 | 27.4% | 2013-04-12 | 25.53% | 2013-04-12 | 22.72% | 2013-05-31 | 31.1% | 2013-05-31 | 26.32%
2013-06-21 | 29.76% | 2013-05-31 | 38.28% | 2013-05-31 | 40.51% | 2013-05-24 | 35.62% | 2013-04-12 | 29.47% | 2013-04-12 | 26.23% | 2013-05-31 | 31.1% | 2013-06-21 | 29.9%
2013-06-28 | 34.52% | 2013-05-31 | 38.28% | 2013-05-31 | 40.51% | 2013-05-31 | 41.1% | 2013-04-26 | 32.11% | 2013-04-26 | 28.57% | 2013-06-07 | 32.3% | 2013-06-28 | 34.69%
2013-06-28 | 35.71% | 2013-06-07 | 39.47% | 2013-06-07 | 41.77% | 2013-05-31 | 43.84% | 2013-04-26 | 34.74% | 2013-04-26 | 30.91% | 2013-06-21 | 34.69% | 2013-06-28 | 35.89%
2013-07-12 | 38.1% | 2013-06-21 | 41.87% | 2013-06-14 | 44.3% | 2013-05-31 | 46.58% | 2013-05-03 | 38.68% | 2013-05-03 | 34.43% | 2013-06-21 | 38.28% | 2013-07-12 | 38.28%
2013-08-02 | 44.05% | 2013-06-21 | 45.45% | 2013-06-21 | 46.84% | 2013-06-07 | 47.95% | 2013-05-10 | 40% | 2013-05-03 | 37.94% | 2013-06-21 | 41.87% | 2013-08-02 | 44.26%
2013-08-09 | 48.81% | 2013-06-21 | 49.04% | 2013-06-21 | 50.63% | 2013-06-21 | 50.68% | 2013-05-24 | 47.89% | 2013-05-10 | 39.11% | 2013-07-19 | 46.65% | 2013-08-09 | 49.04%
2013-08-23 | 52.38% | 2013-07-10 | 56.94% | 2013-07-12 | 59.49% | 2013-06-28 | 54.79% | 2013-05-31 | 51.84% | 2013-05-10 | 43.79% | 2013-07-26 | 52.63% | 2013-08-23 | 52.63%
2013-09-06 | 57.14% | 2013-07-19 | 61.72% | 2013-07-12 | 64.56% | 2013-07-05 | 60.27% | 2013-06-07 | 57.11% | 2013-05-24 | 50.82% | 2013-08-02 | 59.81% | 2013-09-06 | 57.42%
2013-09-27 | 63.1% | 2013-07-26 | 67.7% | 2013-07-19 | 69.62% | 2013-07-12 | 69.86% | 2013-06-07 | 62.37% | 2013-05-31 | 54.33% | 2013-08-23 | 64.59% | 2013-09-27 | 63.4%
2013-10-25 | 71.43% | 2013-08-23 | 72.49% | 2013-08-09 | 73.42% | 2013-07-26 | 73.97% | 2013-06-21 | 65% | 2013-05-31 | 57.85% | 2013-08-30 | 70.57% | 2013-10-25 | 71.77%
2013-11-01 | 77.38% | 2013-08-30 | 78.47% | 2013-08-23 | 79.75% | 2013-08-02 | 79.45% | 2013-07-05 | 70.26% | 2013-05-31 | 62.53% | 2013-09-18 | 78.47% | 2013-11-01 | 77.75%
2013-12-06 | 84.52% | 2013-10-04 | 84.45% | 2013-09-13 | 86.08% | 2013-08-30 | 84.93% | 2013-07-12 | 79.47% | 2013-06-07 | 67.21% | 2013-10-04 | 84.45% | 2013-12-06 | 84.93%
2014-01-24 | 92.86% | 2013-10-11 | 92.82% | 2013-09-27 | 92.41% | 2013-08-30 | 91.78% | 2013-07-12 | 83.42% | 2013-06-07 | 71.9% | 2013-10-11 | 92.82% | 2014-01-22 | 92.82%
2014-03-07 | 100% | 2013-11-22 | 100% | 2013-11-08 | 100% | 2013-10-11 | 100% | 2013-08-02 | 86.84% | 2013-06-21 | 74.24% | 2013-11-22 | 100% | 2014-03-05 | 100%
[8 empty] | 2013-08-09 | 92.11% | 2013-07-05 | 78.92%
[8 empty] | 2013-09-20 | 100% | 2013-07-12 | 87.12%
[10 empty] | 2013-07-12 | 90.63%
[10 empty] | 2013-07-19 | 91.8%
[10 empty] | 2013-07-19 | 92.97%
[10 empty] | 2013-08-30 | 100%

## Efficiency
Design Option | Duration | Efficiency
Simulators | 7.1333 | 22.4%
Infra + Clients Front End | 7.8333 | 20.23%
TopDev2+TopDev1 | 8.5333 | 21%
TopDev2 | 9.4667 | 22%
Normal | 9.9333 | 23%
Sub-Critical | 13.4333 | 18%
Simulators
Infra+Clients
Front-End
TopDev2+
TopDev1
TopDev2
Normal
Subcritical