## Project Plan
ID | Owner | Activity | Duration | Depends on | Planned Completion Date | Planned Earned Value
1 |  | Start | 0 |  | 2015-01-05 | 0%
2 |  | Requirements | 15 |  | 2015-01-23 | 2.655%
3 |  | Architecture | 15 |  | 2015-01-23 | 5.31%
4 |  | Project Planning | 10 |  | 2015-02-06 | 7.08%
5 |  | Management Education | 5 |  | 2015-02-13 | 7.965%
6 |  | SDP Review | 0 |  | 2015-02-13 | 7.965%
8 |  | Dev Training | 5 |  | 2015-02-20 | 8.85%
11 |  | Build and Setup | 10 |  | 2015-02-27 | 10.62%
14 |  | Logging | 10 |  | 2015-03-06 | 12.39%
15 |  | Message Bus | 15 |  | 2015-03-13 | 15.04%
16 |  | Security | 20 |  | 2015-03-20 | 18.58%
17 |  | Infrastructure Done | 0 |  | 2015-03-20 | 18.58%
9 |  | Test Plan | 25 |  | 2015-03-27 | 23.01%
18 |  | Payments DB | 5 |  | 2015-03-27 | 23.89%
19 |  | Members DB | 5 |  | 2015-03-27 | 24.78%
20 |  | Projects DB | 5 |  | 2015-03-27 | 25.66%
21 |  | Contractors DB | 5 |  | 2015-03-27 | 26.55%
7 |  | UX Design | 10 |  | 2015-04-03 | 28.32%
22 |  | Education DB | 5 |  | 2015-04-03 | 29.2%
24 |  | Regulations DB | 5 |  | 2015-04-03 | 30.09%
23 |  | Workflows Repository | 15 |  | 2015-04-10 | 32.74%
25 |  | DB Done | 0 |  | 2015-04-10 | 32.74%
27 |  | Payments Access | 10 |  | 2015-04-24 | 34.51%
28 |  | Members Access | 10 |  | 2015-04-24 | 36.28%
29 |  | Projects Access | 10 |  | 2015-04-24 | 38.05%
10 |  | Test Harness | 25 |  | 2015-05-01 | 42.48%
12 |  | UI Design | 20 |  | 2015-05-01 | 46.02%
30 |  | Contractors Access | 10 |  | 2015-05-08 | 47.79%
31 |  | Education Access | 10 |  | 2015-05-08 | 49.56%
32 |  | Workflows Access | 20 |  | 2015-05-08 | 53.1%
33 |  | Regulations Access | 10 |  | 2015-05-08 | 54.87%
34 |  | RA Done | 0 |  | 2015-05-08 | 54.87%
13 |  | Manual | 20 |  | 2015-05-29 | 58.41%
36 |  | Regulations Engine B | 15 |  | 2015-05-29 | 61.06%
37 |  | Search Engine | 15 |  | 2015-05-29 | 63.72%
26 |  | Data Migration | 10 |  | 2015-06-12 | 65.49%
35 |  | Regulations Engine A | 30 |  | 2015-06-19 | 70.8%
38 |  | Emgines Done | 0 |  | 2015-06-19 | 70.8%
39 |  | Abstract Manager | 30 |  | 2015-06-19 | 76.11%
40 |  | Membership Manager | 10 |  | 2015-07-03 | 77.88%
41 |  | Market Manager | 10 |  | 2015-07-03 | 79.65%
42 |  | Education Manager | 10 |  | 2015-07-03 | 81.42%
43 |  | Regression Test Harness | 10 |  | 2015-07-03 | 83.19%
44 |  | Managers Complete | 0 |  | 2015-07-03 | 83.19%
47 |  | Education Portal | 10 |  | 2015-07-17 | 84.96%
45 |  | Members Portal | 15 |  | 2015-07-24 | 87.61%
46 |  | Contractors Portal | 15 |  | 2015-07-24 | 90.27%
48 |  | Marketplace App | 25 |  | 2015-08-07 | 94.69%
49 |  | Clients Complete | 0 |  | 2015-08-07 | 94.69%
50 |  | Manual Polishing | 10 |  | 2015-08-21 | 96.46%
51 |  | System Testing | 10 |  | 2015-08-21 | 98.23%
52 |  | System Rollout | 10 |  | 2015-09-04 | 100%
|  | Total Planned Effort | 565
|  | Duration | 8.0667

## Staffing
Date | Project Manager | Product Manager | Architect | Developers | DevOps | Test Engineers/UX | Testers | Cost (M/M) | Direct Cost
Start
2015-01-05 | 1 | 1 | 1 |  |  |  |  | 0 | 0
2015-01-23 | 1 | 1 | 1 |  |  |  |  | 1.8 | 1.2
2015-01-26 | 1 | 1 | 1 |  |  |  |  | 0.3 | 0.3
2015-02-06 | 1 | 1 | 1 |  |  |  |  | 1.1 | 1.1
2015-02-09 | 1 | 1 | 1 |  |  |  |  | 0.3 | 0.3
2015-02-13 | 1 | 1 | 1 |  |  |  |  | 0.4 | 0.4
2015-02-16 | 1 | 1 | 1 |  | 1 |  | 1 | 0.5 | 0.2
2015-02-20 | 1 | 1 | 1 |  | 1 |  | 1 | 0.66667 | 0.26667
2015-02-23 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0.8 | 0.5 | 6
2015-02-27 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.0667 | 0.66667 | 8
2015-03-06 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.8667 | 0.93333 | 14
2015-03-13 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.8667 | 0.93333 | 14
2015-03-20 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.8667 | 0.7 | 14
2015-03-23 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1.1 | 0.7 | 12
2015-03-27 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1.4667 | 0.93333 | 16
2015-03-30 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1.1 | 0.7 | 12
2015-04-03 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1.4667 | 0.93333 | 16
2015-04-06 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1.1 | 0.7 | 12
2015-04-10 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1.4667 | 0.93333 | 16
2015-04-13 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1.1 | 0.6 | 12
2015-04-24 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 4.0333 | 2.2 | 44
2015-04-27 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1.1 | 0.6 | 12
2015-05-01 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1.4667 | 0.8 | 16
2015-05-04 | 1 | 1 | 1 | 4 | 1 |  | 1 | 0.9 | 0.5 | 12
2015-05-08 | 1 | 1 | 1 | 4 | 1 |  | 1 | 1.2 | 0.66667 | 16
2015-05-11 | 1 | 1 | 1 | 4 | 1 |  | 1 | 0.9 | 0.5 | 12
2015-05-29 | 1 | 1 | 1 | 4 | 1 |  | 1 | 5.4 | 3 | 72
2015-06-01 | 1 | 1 | 1 | 4 | 1 |  | 1 | 0.9 | 0.4 | 12
2015-06-12 | 1 | 1 | 1 | 4 | 1 |  | 1 | 3.3 | 1.4667 | 44
2015-06-19 | 1 | 1 | 1 | 4 | 1 |  | 1 | 2.1 | 0.93333 | 28
2015-06-22 | 1 | 1 | 1 | 4 | 1 |  | 1 | 0.9 | 0.4 | 12
2015-07-03 | 1 | 1 | 1 | 4 | 1 |  | 1 | 3.3 | 1.4667 | 44
2015-07-06 | 1 | 1 | 1 | 4 | 1 |  | 1 | 0.9 | 0.4 | 12
2015-07-17 | 1 | 1 | 1 | 4 | 1 |  | 1 | 3.3 | 1.4667 | 44
2015-07-24 | 1 | 1 | 1 | 3 | 1 |  | 1 | 1.8667 | 0.7 | 21
2015-08-07 | 1 | 1 | 1 | 1 | 1 |  | 1 | 2.8 | 0.46667 | 14
2015-08-10 | 1 | 1 | 1 |  | 1 |  | 2 | 0.6 | 0.3
2015-08-21 | 1 | 1 | 1 |  | 1 |  | 2 | 2.2 | 1.1
2015-08-24 | 1 | 1 | 1 |  | 1 |  | 1 | 0.5 | 0.4 |  | Average Devs: | 3.4364
2015-09-04 | 1 | 1 | 1 |  | 1 |  | 1 | 1.8333 | 1.4667 |  | Average Staff: | 7.5413 | 68.56%
[7 empty] | Total | 60.8333 | 32.2333
28.6

## Summary
Overall
Cost in man months | 60.8333
Duration in months | 8.0667
Average staffing | 7.5413
Effort in estimated MM | 18.8333
Efficiency | 30.96%
Front End | 16.12%

## Complexity
ID | Activity | Depends on | Reduced Dependencies | Number of Dependencies Per Acticity |  |  | All Activities | Pulses Only
1 | Start |  |  |  | P |  | 1 | 1
2 | Requirements | 1 | 1 | 1 | N | Number of Activities | 6 | 6
3 | Architecture | 1 | 1 | 1 | E | Total Dependencies | 6 | 6
4 | Project Planning | 3 | 3 | 1
5 | Management Education | 4 | 4 | 1 | C | Complexity | 2 | 2
6 | SDP Review | 5,2 | 5,2 | 2
8 | Dev Training | 6 | 6 | 1
11 | Build and Setup | 6 | 6 | 1
9 | Test Plan | 8 | 8 | 1 | P |  | 1 | 1
14 | Logging | 8 | 8 | 1 | N | Number of Activities | 8 | 7
15 | Message Bus | 8 | 8 | 1 | E | Total Dependencies | 10 | 9
16 | Security | 8 | 8 | 1
17 | Infrastructure Complete | 16,15,14,11 | 16,15,14,11 | 4 | C | Complexity | 4 | 4
7 | UX Design | 17 | 17 | 1
18 | Payments DB | 17 | 17 | 1
19 | Members DB | 17 | 17 | 1
20 | Projects DB | 17 | 17 | 1
21 | Contractors DB | 17 | 17 | 1
23 | Workflows Repository | 17 | 17 | 1
10 | Test Harness | 9 | 9 | 1 | P |  | 1 | 1
22 | Education DB | 17,18 | 18 | 1 | N | Number of Activities | 12 | 9
24 | Regulations DB | 17,19 | 19 | 1 | E | Total Dependencies | 15 | 12
12 | UI Design | 7 | 7 | 1 |  |  |  | 0
25 | DB Complete | 18,19,20,21,22,23,24 | 20,21,22,23,24 | 5 | C | Complexity | 5 | 5
27 | Payments Access | 25 | 25 | 1
28 | Members Access | 25 | 25 | 1
29 | Projects Access | 25 | 25 | 1
32 | Workflows Access | 25 | 25 | 1
30 | Contractors Access | 25,27 | 27 | 1 | P |  | 1 | 1
31 | Education Access | 25,28 | 28 | 1 | N | Number of Activities | 10 | 9
33 | Regulations Access | 25,29 | 29 | 1 | E | Total Dependencies | 12 | 11
13 | Manual | 12 | 12 | 1
34 | RA Complete | 27,28,29,30,31,32,33 | 30,31,32,33 | 4 | C | Complexity | 4 | 4
35 | Regulations Engine A | 34 | 34 | 1 |  |  |  | 0
36 | Regulations Engine B | 34 | 34 | 1 | P |  | 1 | 1
37 | Search Engine | 34 | 34 | 1 | N | Number of Activities | 7 | 6
39 | Abstract Manager | 34 | 34 | 1 | E | Total Dependencies | 9 | 8
26 | Data Migration | 25,37 | 37 | 1
38 | Emgines Complete | 35,36,37,39 | 35,36,37,39 | 4 | C | Complexity | 4 | 4
40 | Membership Manager | 34,38 | 38 | 1 | P |  | 1 | 1
41 | Market Manager | 34,39 | 38 | 1 | N | Number of Activities | 6 | 6
42 | Education Manager | 34,40 | 38 | 1 | E | Total Dependencies | 8 | 8
43 | Regression Test Harness | 34,41 | 38 | 1
44 | Managers Complete | 40,41,42,43 | 40,41,42,43 | 4 | C | Complexity | 4 | 4
45 | Members Portal | 12,44 | 12,44 | 2 | P |  | 1 | 1
46 | Contractors Portal | 12,44 | 12,44 | 2 | N | Number of Activities | 6 | 6
47 | Education Portal | 12,44 | 12,44 | 2 | E | Total Dependencies | 12 | 8
48 | Marketplace App | 12,44 | 12,44 | 2
49 | Clients Complete | 45,46,47,48 | 45,46,47,48 | 4 | C | Complexity | 8 | 4
50 | Manual Polishing | 49 | 49 | 1 | P |  | 1 | 1
51 | System Testing | 10,49 | 10,49 | 2 | N | Number of Activities | 4 | 4
52 | System Rollout | 26,13,51,50 | 26,13,51,50 | 4 | E | Total Dependencies | 7 | 4
[5 empty] | C | Complexity | 5 | 2