## D1
[12 empty] | Phi = | 1.618
ID | Activity | Total Float | Geometric Float | Critical | Red | Yellow | Green | Criticality Risk | 0.26706 | Activity Risk | 0.49846 |  | Fibonacci Risk | 0.25287
1 | Requirements | 75 | 76 | 0 | 0 | 0 | 1
2 | Architecture | 75 | 76 | 0 | 0 | 0 | 1 | Critical factor | 4
3 | Project Design | 75 | 76 | 0 | 0 | 0 | 1 | Red Factor | 3
4 | Test Plan | 140 | 141 | 0 | 0 | 0 | 1 | Yellow Factor | 2
5 | Test Harness | 140 | 141 | 0 | 0 | 0 | 1 | Green Factor | 1
6 | Logging | 75 | 76 | 0 | 0 | 0 | 1
7 | Security | 75 | 76 | 0 | 0 | 0 | 1 | Total | 10
8 | Pub/Sub | 90 | 91 | 0 | 0 | 0 | 1
9 | Resource A | 100 | 101 | 0 | 0 | 0 | 1
10 | Resource B | 105 | 106 | 0 | 0 | 0 | 1 | Red Limit | 9
11 | Resource Access A | 100 | 101 | 0 | 0 | 0 | 1 | Yellow Limit | 26
12 | Resource Access B | 85 | 86 | 0 | 0 | 0 | 1
13 | Resource Access C | 75 | 76 | 0 | 0 | 0 | 1
14 | EngineA | 80 | 81 | 0 | 0 | 0 | 1
15 | EngineB | 75 | 76 | 0 | 0 | 0 | 1
16 | EngineC | 105 | 106 | 0 | 0 | 0 | 1 | Sanity Check: | Passed
17 | ManagerA | 75 | 76 | 0 | 0 | 0 | 1
18 | ManagerB | 80 | 81 | 0 | 0 | 0 | 1
19 | Client App1 | 80 | 81 | 0 | 0 | 0 | 1
20 | Client App2 | 75 | 76 | 0 | 0 | 0 | 1
21 | System Testing | 0 | 1 | 1 | 0 | 0 | 0 | Decompressed start date for System Testing: |  | 2014-01-27

## D2
[12 empty] | Phi = | 1.618
ID | Activity | Total Float | Geometric Float | Critical | Red | Yellow | Green | Criticality Risk | 0.26706 | Activity Risk | 0.57891 |  | Fibonacci Risk | 0.25287
1 | Requirements | 45 | 46 | 0 | 0 | 0 | 1
2 | Architecture | 45 | 46 | 0 | 0 | 0 | 1 | Critical factor | 4
3 | Project Design | 45 | 46 | 0 | 0 | 0 | 1 | Red Factor | 3
4 | Test Plan | 110 | 111 | 0 | 0 | 0 | 1 | Yellow Factor | 2
5 | Test Harness | 110 | 111 | 0 | 0 | 0 | 1 | Green Factor | 1
6 | Logging | 45 | 46 | 0 | 0 | 0 | 1
7 | Security | 45 | 46 | 0 | 0 | 0 | 1 | Total | 10
8 | Pub/Sub | 60 | 61 | 0 | 0 | 0 | 1
9 | Resource A | 70 | 71 | 0 | 0 | 0 | 1
10 | Resource B | 75 | 76 | 0 | 0 | 0 | 1 | Red Limit | 9
11 | Resource Access A | 70 | 71 | 0 | 0 | 0 | 1 | Yellow Limit | 26
12 | Resource Access B | 55 | 56 | 0 | 0 | 0 | 1
13 | Resource Access C | 45 | 46 | 0 | 0 | 0 | 1
14 | EngineA | 50 | 51 | 0 | 0 | 0 | 1
15 | EngineB | 45 | 46 | 0 | 0 | 0 | 1
16 | EngineC | 75 | 76 | 0 | 0 | 0 | 1 | Sanity Check: | Passed
17 | ManagerA | 45 | 46 | 0 | 0 | 0 | 1
18 | ManagerB | 50 | 51 | 0 | 0 | 0 | 1
19 | Client App1 | 50 | 51 | 0 | 0 | 0 | 1
20 | Client App2 | 45 | 46 | 0 | 0 | 0 | 1
21 | System Testing | 0 | 1 | 1 | 0 | 0 | 0 | Decompressed start date for System Testing: |  | 2014-01-27

## D3
[12 empty] | Phi = | 1.618
ID | Activity | Total Float | Geometric Float | Critical | Red | Yellow | Green | Criticality Risk | 0.39685 | Activity Risk | 0.70292 |  | Fibonacci Risk | 0.3329
1 | Requirements | 20 | 21 | 0 | 0 | 1 | 0
2 | Architecture | 20 | 21 | 0 | 0 | 1 | 0 | Critical factor | 4
3 | Project Design | 20 | 21 | 0 | 0 | 1 | 0 | Red Factor | 3
4 | Test Plan | 85 | 86 | 0 | 0 | 0 | 1 | Yellow Factor | 2
5 | Test Harness | 85 | 86 | 0 | 0 | 0 | 1 | Green Factor | 1
6 | Logging | 20 | 21 | 0 | 0 | 1 | 0
7 | Security | 20 | 21 | 0 | 0 | 1 | 0 | Total | 10
8 | Pub/Sub | 35 | 36 | 0 | 0 | 0 | 1
9 | Resource A | 45 | 46 | 0 | 0 | 0 | 1
10 | Resource B | 50 | 51 | 0 | 0 | 0 | 1 | Red Limit | 9
11 | Resource Access A | 45 | 46 | 0 | 0 | 0 | 1 | Yellow Limit | 26
12 | Resource Access B | 30 | 31 | 0 | 0 | 0 | 1
13 | Resource Access C | 20 | 21 | 0 | 0 | 1 | 0
14 | EngineA | 25 | 26 | 0 | 0 | 1 | 0
15 | EngineB | 20 | 21 | 0 | 0 | 1 | 0
16 | EngineC | 50 | 51 | 0 | 0 | 0 | 1 | Sanity Check: | Passed
17 | ManagerA | 20 | 21 | 0 | 0 | 1 | 0
18 | ManagerB | 25 | 26 | 0 | 0 | 1 | 0
19 | Client App1 | 25 | 26 | 0 | 0 | 1 | 0
20 | Client App2 | 20 | 21 | 0 | 0 | 1 | 0
21 | System Testing | 0 | 1 | 1 | 0 | 0 | 0 | Decompressed start date for System Testing: |  | 2014-01-27

## D4
[12 empty] | Phi = | 1.618
ID | Activity | Total Float | Geometric Float | Critical | Red | Yellow | Green | Criticality Risk | 0.42393 | Activity Risk | 0.7871 |  | Fibonacci Risk | 0.34851
1 | Requirements | 10 | 11 | 0 | 0 | 1 | 0
2 | Architecture | 10 | 11 | 0 | 0 | 1 | 0 | Critical factor | 4
3 | Project Design | 10 | 11 | 0 | 0 | 1 | 0 | Red Factor | 3
4 | Test Plan | 75 | 76 | 0 | 0 | 0 | 1 | Yellow Factor | 2
5 | Test Harness | 75 | 76 | 0 | 0 | 0 | 1 | Green Factor | 1
6 | Logging | 10 | 11 | 0 | 0 | 1 | 0
7 | Security | 10 | 11 | 0 | 0 | 1 | 0 | Total | 10
8 | Pub/Sub | 25 | 26 | 0 | 0 | 1 | 0
9 | Resource A | 35 | 36 | 0 | 0 | 0 | 1
10 | Resource B | 40 | 41 | 0 | 0 | 0 | 1 | Red Limit | 9
11 | Resource Access A | 35 | 36 | 0 | 0 | 0 | 1 | Yellow Limit | 26
12 | Resource Access B | 20 | 21 | 0 | 0 | 1 | 0
13 | Resource Access C | 10 | 11 | 0 | 0 | 1 | 0
14 | EngineA | 15 | 16 | 0 | 0 | 1 | 0
15 | EngineB | 10 | 11 | 0 | 0 | 1 | 0
16 | EngineC | 40 | 41 | 0 | 0 | 0 | 1 | Sanity Check: | Passed
17 | ManagerA | 10 | 11 | 0 | 0 | 1 | 0
18 | ManagerB | 15 | 16 | 0 | 0 | 1 | 0
19 | Client App1 | 15 | 16 | 0 | 0 | 1 | 0
20 | Client App2 | 10 | 11 | 0 | 0 | 1 | 0
21 | System Testing | 0 | 1 | 1 | 0 | 0 | 0 | Decompressed start date for System Testing: |  | 2014-01-27