## Activities
Max Resources Per Task | 1 | Tracking Resolution | 7
|  |  |  | Start Date |  | Actual Progress |  | Actual Effort | Actual Progress |  | Actual Effort | Actual Progress |  | Actual Effort | Actual Progress |  | Actual Effort | Actual Progress |  | Actual Effort | Actual Progress |  | Actual Effort | Actual Progress |  | Actual Effort | Actual Progress |  | Actual Effort
Owner | Activity | Estimated Duration | % | 2020-01-06 |  | 2020-01-10 |  | 2020-01-10 | 2020-01-17 |  | 2020-01-17 | 2020-01-24 |  | 2020-01-24 | 2020-01-31 |  | 2020-01-31 | 2020-02-07 |  | 2020-02-07 | 2020-02-14 |  | 2020-02-14 | 2020-02-21 |  | 2020-02-21 | 2020-02-28 |  | 2020-02-28
ARC | Fuzzy Front End | 20 | 100%
| System Design | 5 | 25% | 0 | 0 | 1 | 5 | 5 | 1 | 5 |  | 1 | 5 |  | 1 | 5 |  | 1 | 5 |  | 1 | 5 |  | 1 | 5 |  | 1 | 5
| Project Design | 5 | 25% | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 5 | 1 | 5 |  | 1 | 5 |  | 1 | 5 |  | 1 | 5 |  | 1 | 5 |  | 1 | 5
| Documentation | 5 | 25% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 1 | 5 | 5 | 1 | 5 |  | 1 | 5 |  | 1 | 5 |  | 1 | 5 |  | 1 | 5
| Prepare fpr SDP Review | 5 | 25% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 5 | 1 | 5 | 5 | 1 | 5 |  | 1 | 5 |  | 1 | 5
| SDP Review | 0 | 0% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 1 | 0
STE | Test Plan | 15 | 100%
| Test Cases | 5 | 33.33% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 5 | 1 | 5 | 5 | 1 | 5 |  | 1 | 5
| Test matrix | 5 | 33.33% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1 | 5 | 5 | 1 | 5
| Automation plan | 5 | 33.33% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1 | 5 | 5
STE | Test Harness | 10 | 100%
| Construction | 5 | 50% | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Regression | 5 | 50% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
DEV | Logging | 15 | 100%
| Requirements | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 5 | 1 | 3 | 5 | 1 | 3 |  | 1 | 3
| Test Plan | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1 | 3 | 5 | 1 | 3
| Detailed Design | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 1 | 3 | 5
| Construction | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Testing + Integration | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
DEV | Security | 15 | 100%
| Requirements | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Test Plan | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Detailed Design | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Construction | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Testing + Integration | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
DEV | Pub/Sub | 15 | 100%
| Requirements | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Test Plan | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Detailed Design | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Construction | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Testing + Integration | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
DEV | Resource Access 1 | 15 | 100%
| Requirements | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Test Plan | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Detailed Design | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Construction | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Testing + Integration | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
DEV | Resource Access 2 | 15 | 100%
| Requirements | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Test Plan | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Detailed Design | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Construction | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Testing + Integration | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
DEV | Resource Access 3 | 15 | 100%
| Requirements | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Test Plan | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Detailed Design | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Construction | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Testing + Integration | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
DEV | EngineA | 15 | 100%
| Requirements | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Test Plan | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Detailed Design | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Construction | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Testing + Integration | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
DEV | EngineB | 15 | 100%
| Requirements | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Test Plan | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Detailed Design | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Construction | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Testing + Integration | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
DEV | EngineC | 15 | 100%
| Requirements | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Test Plan | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Detailed Design | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Construction | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Testing + Integration | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
DEV | ManagerA | 15 | 100%
| Requirements | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Test Plan | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Detailed Design | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Construction | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Testing + Integration | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
|  |  |  | 0 | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
DEV | ManagerB | 15 | 100%
| Requirements | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Test Plan | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Detailed Design | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Construction | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Testing + Integration | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
DEV | Client App1 | 15 | 100%
| Requirements | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Test Plan | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Detailed Design | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Construction | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Testing + Integration | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
DEV | Client App2 | 15 | 100%
| Requirements | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Test Plan | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Detailed Design | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Construction | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Testing + Integration | 3 | 20% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
QC | System Testing | 15 | 100%
| Integration | 8 | 53.33% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
| Deployment | 7 | 46.67% | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
STE - Software Test Engineer
QC - Quality Control (often incorrectly referred to as QA)
DEV - Developer
Formulas:
Actual Progress = [Start Date]+4
Actual Progress = [Actual Progress]+D1
Actual Effort = [Actual Progress]
Note on U8: Juval Lowy: Suppose this took twice as long
Note on AA10: Juval Lowy: Milestone, no effort
Note on AA13: Juval Lowy: STE is already here, waiting
Note on AA22: Juval Lowy: DEV is already here, waiting

## Project Plan
ID | Owner | Activity | Duration | Depends on | Planned Completion Date | Plan
|  | Start |  |  | 2020-01-06 | 0%
1 | ARC | Fuzzy Front End | 20 |  | 2020-01-31 | 7.843%
2 |  | SDP Review | 0 | 1 | 2020-01-31 | 7.843%
3 | STE | Test Plan | 15 | 2 | 2020-02-21 | 13.73%
5 | DEV | Logging | 15 | 2 | 2020-02-21 | 19.61%
4 | STE | Test Harness | 10 | 3 | 2020-03-06 | 23.53%
6 | DEV | Security | 15 | 5 | 2020-03-13 | 29.41%
7 | DEV | Pub/Sub | 15 | 6 | 2020-04-03 | 35.29%
8 | DEV | Resource Access 1 | 15 | 7 | 2020-04-24 | 41.18%
9 | DEV | Resource Access 2 | 15 | 8 | 2020-05-15 | 47.06%
10 | DEV | Resource Access 3 | 15 | 9 | 2020-06-05 | 52.94%
11 | DEV | EngineA | 15 | 10 | 2020-06-26 | 58.82%
12 | DEV | EngineB | 15 | 11 | 2020-07-17 | 64.71%
13 | DEV | EngineC | 15 | 12 | 2020-08-07 | 70.59%
14 | DEV | ManagerA | 15 | 13 | 2020-08-28 | 76.47%
15 | DEV | ManagerB | 15 | 14 | 2020-09-18 | 82.35%
16 | DEV | Client App1 | 15 | 15 | 2020-10-09 | 88.24%
17 | DEV | Client App2 | 15 | 16 | 2020-10-30 | 94.12%
18 | QC | System Testing | 15 | 17,4 | 2020-11-20 | 100%
|  | Total Planned Effort | 255
Note on A10: Juval Lowy: Note: These are sorted by completion date, not by IDs

## Progress and Effort
Date | Progress | Effort
2020-01-06 | 0% | 0%
2020-01-10 | 1.961% | 1.961%
2020-01-17 | 3.922% | 3.922%
2020-01-24 | 5.882% | 5.882%
2020-01-31 | 5.882% | 7.843%
2020-02-07 | 7.843% | 13.73%
2020-02-14 | 10.98% | 17.65%
2020-02-21 | 14.12% | 21.57%
2020-02-28 | 17.25% | 25.49%