## Time-Cost Curve Data
Design Option | Duration | Total Cost | Direct Cost | Indirect Cost | % Time From Boradband | % Cost From Boradband
Compressed | 7.1333 | 58.5 | 36.6667 | 21.8333 | 47.2% | 27.52%
By Dependencies | 7.8333 | 58.9667 | 32 | 26.9667 | 34.04% | 26.51%
By Layers | 8.0667 | 60.8333 | 32.2333 | 28.6 | 30.17% | 22.63%
By Layers Subcritical | 11.1 | 74.1333 | 30.3667 | 43.7667 | 5.405% | 0.6295%
By Layers Subcritical D1 | 11.8 | 79.5446 | 31.7667 | 47.7779 | 11.02% | 6.216%

## Time-Cost Curve (Model)
Direct Cost |  |  | Indirect Cost |  | Total Cost
a | 1.2019 |  | a | 5.3529 | a | 1.2019
b | -23.4639 |  | b | -15.3868 | b | -18.1109
c | 142.7442 |  |  |  | c | 127.3574
Duration | Direct Cost | Indirect Cost | Total Cost
6 | 45.2278 | 16.7309 | 61.9587
6.2 | 43.4675 | 17.8015 | 61.269
6.4 | 41.8034 | 18.8721 | 60.6755
6.6 | 40.2355 | 19.9426 | 60.1781
6.8 | 38.7637 | 21.0132 | 59.7769
7 | 37.3881 | 22.0838 | 59.4719
7.2 | 36.1086 | 23.1544 | 59.263
7.4 | 34.9252 | 24.225 | 59.1502
7.6 | 33.838 | 25.2956 | 59.1336
7.8 | 32.847 | 26.3662 | 59.2131
8 | 31.9521 | 27.4368 | 59.3888
8.2 | 31.1533 | 28.5074 | 59.6606
8.4 | 30.4507 | 29.5779 | 60.0286
8.6 | 29.8442 | 30.6485 | 60.4928
8.8 | 29.3339 | 31.7191 | 61.053
9 | 28.9198 | 32.7897 | 61.7095
9.2 | 28.6017 | 33.8603 | 62.462
9.4 | 28.3799 | 34.9309 | 63.3108
9.6 | 28.2542 | 36.0015 | 64.2556
9.8 | 28.2246 | 37.0721 | 65.2967
10 | 28.2912 | 38.1426 | 66.4338
10.2 | 28.4539 | 39.2132 | 67.6672
10.4 | 28.7128 | 40.2838 | 68.9966
10.6 | 29.0678 | 41.3544 | 70.4222
10.8 | 29.519 | 42.425 | 71.944
11 | 30.0663 | 43.4956 | 73.5619
11.2 | 30.7098 | 44.5662 | 75.276
11.4 | 31.4494 | 45.6368 | 77.0862
11.6 | 32.2852 | 46.7074 | 78.9926
11.8 | 33.2171 | 47.7779 | 80.9951
12 | 34.2452 | 48.8485 | 83.0937
12.2 | 35.3694 | 49.9191 | 85.2885 |  |  | Broadband
12.4 | 36.5898 | 50.9897 | 87.5795 |  |  | 10.5 | 74.6

## Project Plans
Compressed |  | By Dependencies |  | Subcritical |  | By Layers |  | By Layers Subcritical
Planned Completion Date | Planned Earned Value | Planned Completion Date | Planned Earned Value | Planned Completion Date | Planned Earned Value | Planned Completion Date | Planned Earned Value | Planned Completion Date | Planned Earned Value
2015-01-05 | 0% | 2015-01-05 | 0% | 2015-01-05 | 0% | 2015-01-05 | 0% | 2015-01-05 | 0%
2015-01-23 | 2.308% | 2015-01-23 | 2.655% | 2015-01-23 | 2.655% | 2015-01-23 | 2.655% | 2015-01-23 | 2.655%
2015-01-23 | 4.615% | 2015-01-23 | 5.31% | 2015-01-23 | 5.31% | 2015-01-23 | 5.31% | 2015-01-23 | 5.31%
2015-02-06 | 6.154% | 2015-02-06 | 7.08% | 2015-02-06 | 7.08% | 2015-02-06 | 7.08% | 2015-02-06 | 7.08%
2015-02-13 | 6.923% | 2015-02-13 | 7.965% | 2015-02-13 | 7.965% | 2015-02-13 | 7.965% | 2015-02-13 | 7.965%
2015-02-20 | 7.692% | 2015-02-13 | 7.965% | 2015-02-13 | 7.965% | 2015-02-13 | 7.965% | 2015-02-13 | 7.965%
2015-02-20 | 8.462% | 2015-02-20 | 8.85% | 2015-02-20 | 8.85% | 2015-02-20 | 8.85% | 2015-02-20 | 8.85%
2015-02-27 | 10% | 2015-02-27 | 10.62% | 2015-02-27 | 10.62% | 2015-02-27 | 10.62% | 2015-02-27 | 10.62%
2015-02-27 | 11.54% | 2015-03-06 | 12.39% | 2015-03-06 | 12.39% | 2015-03-06 | 12.39% | 2015-03-06 | 12.39%
2015-02-27 | 12.31% | 2015-03-13 | 15.04% | 2015-03-13 | 15.04% | 2015-03-13 | 15.04% | 2015-03-13 | 15.04%
2015-03-06 | 13.85% | 2015-03-20 | 18.58% | 2015-03-20 | 18.58% | 2015-03-20 | 18.58% | 2015-03-20 | 18.58%
2015-03-06 | 14.62% | 2015-03-20 | 18.58% | 2015-03-20 | 18.58% | 2015-03-20 | 18.58% | 2015-03-20 | 18.58%
2015-03-06 | 16.15% | 2015-03-27 | 23.01% | 2015-03-27 | 23.01% | 2015-03-27 | 23.01% | 2015-03-27 | 23.01%
2015-03-13 | 18.46% | 2015-03-27 | 23.89% | 2015-03-27 | 23.89% | 2015-03-27 | 23.89% | 2015-03-27 | 23.89%
2015-03-13 | 19.23% | 2015-04-03 | 25.66% | 2015-04-03 | 25.66% | 2015-03-27 | 24.78% | 2015-03-27 | 24.78%
2015-03-13 | 20.77% | 2015-04-03 | 26.55% | 2015-04-03 | 26.55% | 2015-03-27 | 25.66% | 2015-04-03 | 26.55%
2015-03-20 | 21.54% | 2015-04-03 | 29.2% | 2015-04-03 | 29.2% | 2015-03-27 | 26.55% | 2015-04-03 | 27.43%
2015-03-27 | 25.38% | 2015-04-10 | 30.09% | 2015-04-10 | 30.09% | 2015-04-03 | 28.32% | 2015-04-03 | 28.32%
2015-03-27 | 26.15% | 2015-04-10 | 31.86% | 2015-04-10 | 31.86% | 2015-04-03 | 29.2% | 2015-04-10 | 29.2%
2015-03-27 | 27.69% | 2015-04-17 | 32.74% | 2015-04-17 | 32.74% | 2015-04-03 | 30.09% | 2015-04-10 | 31.86%
2015-03-27 | 30% | 2015-04-17 | 34.51% | 2015-04-24 | 33.63% | 2015-04-10 | 32.74% | 2015-04-10 | 32.74%
2015-04-03 | 33.08% | 2015-04-24 | 35.4% | 2015-05-01 | 38.05% | 2015-04-10 | 32.74% | 2015-04-10 | 32.74%
2015-04-03 | 35.38% | 2015-04-24 | 37.17% | 2015-05-01 | 41.59% | 2015-04-24 | 34.51% | 2015-04-24 | 34.51%
2015-04-03 | 36.92% | 2015-05-01 | 41.59% | 2015-05-01 | 42.48% | 2015-04-24 | 36.28% | 2015-05-01 | 38.94%
2015-04-10 | 38.46% | 2015-05-01 | 45.13% | 2015-05-01 | 46.02% | 2015-04-24 | 38.05% | 2015-05-01 | 42.48%
2015-04-10 | 40% | 2015-05-01 | 46.02% | 2015-05-15 | 47.79% | 2015-05-01 | 42.48% | 2015-05-08 | 44.25%
2015-04-10 | 40.77% | 2015-05-01 | 47.79% | 2015-05-15 | 49.56% | 2015-05-01 | 46.02% | 2015-05-08 | 47.79%
2015-04-10 | 41.54% | 2015-05-01 | 51.33% | 2015-05-22 | 54.87% | 2015-05-08 | 47.79% | 2015-05-22 | 49.56%
2015-04-17 | 43.08% | 2015-05-15 | 53.1% | 2015-05-29 | 58.41% | 2015-05-08 | 49.56% | 2015-05-22 | 51.33%
2015-04-17 | 43.85% | 2015-05-15 | 54.87% | 2015-06-05 | 60.18% | 2015-05-08 | 53.1% | 2015-05-29 | 54.87%
2015-04-17 | 44.62% | 2015-05-15 | 57.52% | 2015-06-05 | 62.83% | 2015-05-08 | 54.87% | 2015-06-05 | 56.64%
2015-05-01 | 48.46% | 2015-05-22 | 62.83% | 2015-06-19 | 64.6% | 2015-05-08 | 54.87% | 2015-06-05 | 58.41%
2015-05-01 | 51.54% | 2015-05-29 | 66.37% | 2015-07-03 | 66.37% | 2015-05-29 | 58.41% | 2015-06-19 | 60.18%
2015-05-08 | 54.62% | 2015-05-29 | 68.14% | 2015-07-24 | 69.03% | 2015-05-29 | 61.06% | 2015-06-19 | 60.18%
2015-05-08 | 56.92% | 2015-06-12 | 70.8% | 2015-07-31 | 74.34% | 2015-05-29 | 63.72% | 2015-07-31 | 65.49%
2015-05-08 | 59.23% | 2015-06-12 | 76.11% | 2015-08-07 | 76.11% | 2015-06-12 | 65.49% | 2015-07-31 | 70.8%
2015-05-08 | 61.54% | 2015-06-26 | 77.88% | 2015-08-14 | 77.88% | 2015-06-19 | 70.8% | 2015-08-21 | 73.45%
2015-05-22 | 66.15% | 2015-06-26 | 79.65% | 2015-08-21 | 79.65% | 2015-06-19 | 70.8% | 2015-08-21 | 76.11%
2015-05-29 | 68.46% | 2015-06-26 | 81.42% | 2015-08-28 | 81.42% | 2015-06-19 | 76.11% | 2015-08-21 | 76.11%
2015-06-05 | 71.54% | 2015-06-26 | 83.19% | 2015-09-04 | 83.19% | 2015-07-03 | 77.88% | 2015-09-04 | 77.88%
2015-06-12 | 73.85% | 2015-06-26 | 83.19% | 2015-09-04 | 83.19% | 2015-07-03 | 79.65% | 2015-09-04 | 79.65%
2015-06-12 | 78.46% | 2015-07-10 | 84.96% | 2015-09-25 | 85.84% | 2015-07-03 | 81.42% | 2015-09-18 | 81.42%
2015-06-12 | 82.31% | 2015-07-17 | 87.61% | 2015-10-09 | 87.61% | 2015-07-03 | 83.19% | 2015-09-18 | 83.19%
2015-06-19 | 84.62% | 2015-07-17 | 90.27% | 2015-10-09 | 92.04% | 2015-07-03 | 83.19% | 2015-09-18 | 83.19%
2015-06-26 | 86.15% | 2015-07-31 | 94.69% | 2015-10-30 | 94.69% | 2015-07-17 | 84.96% | 2015-10-09 | 85.84%
2015-06-26 | 87.69% | 2015-08-14 | 96.46% | 2015-11-13 | 96.46% | 2015-07-24 | 87.61% | 2015-10-23 | 90.27%
2015-06-26 | 89.23% | 2015-08-14 | 98.23% | 2015-11-13 | 98.23% | 2015-07-24 | 90.27% | 2015-10-30 | 92.92%
2015-06-26 | 90.77% | 2015-08-28 | 100% | 2015-11-27 | 100% | 2015-08-07 | 94.69% | 2015-11-06 | 94.69%
2015-07-03 | 92.31% |  |  |  |  | 2015-08-07 | 94.69% | 2015-11-06 | 94.69%
2015-07-03 | 93.08% |  |  |  |  | 2015-08-21 | 96.46% | 2015-11-20 | 96.46%
2015-07-03 | 93.85% |  |  |  |  | 2015-08-21 | 98.23% | 2015-11-20 | 98.23%
2015-07-03 | 94.62% |  |  |  |  | 2015-09-04 | 100% | 2015-12-04 | 100%
2015-07-10 | 95.38%
2015-07-10 | 96.92%
2015-07-24 | 98.46%
2015-08-07 | 100%

## Efficiency
Design Option | Duration | Efficiency
Compressed | 7.1333 | 37.04%
By Dependencies | 7.8333 | 31.94%
By Layers | 8.0667 | 30.96%
By Layers Subcritical | 11.1 | 25.4%
| Average | 31.33%
Average