## Project Plan
ID | Activity | Duration | Depends on | Planned Completion Date | Planned Earned Value
| Start | 0 |  | 2015-01-05 | 0%
1 | Requirements | 15 |  | 2015-01-23 | 2.308%
2 | Architecture | 15 |  | 2015-01-23 | 4.615%
3 | Project Planning | 10 |  | 2015-02-06 | 6.154%
4 | Management Education | 5 |  | 2015-02-13 | 6.923%
6 | Dev Training | 5 |  | 2015-02-20 | 7.692%
16 | Members DB | 5 |  | 2015-02-20 | 8.462%
5 | UX Design | 10 |  | 2015-02-27 | 10%
9 | Build and Setup | 10 |  | 2015-02-27 | 11.54%
18 | Contractors DB | 5 |  | 2015-02-27 | 12.31%
12 | Logging | 10 |  | 2015-03-06 | 13.85%
17 | Projects DB | 5 |  | 2015-03-06 | 14.62%
24 | Members Access | 10 |  | 2015-03-06 | 16.15%
13 | Message Bus | 15 |  | 2015-03-13 | 18.46%
15 | Payments DB | 5 |  | 2015-03-13 | 19.23%
26 | Contractors Access | 10 |  | 2015-03-13 | 20.77%
19 | Education DB | 5 |  | 2015-03-20 | 21.54%
7 | Test Plan | 25 |  | 2015-03-27 | 25.38%
21 | Regulations DB | 5 |  | 2015-03-27 | 26.15%
25 | Projects Access | 10 |  | 2015-03-27 | 27.69%
31 | Search Engine | 15 |  | 2015-03-27 | 30%
14 | Security | 20 |  | 2015-04-03 | 33.08%
20 | Workflows Repository | 15 |  | 2015-04-03 | 35.38%
27 | Education Access | 10 |  | 2015-04-03 | 36.92%
23 | Payments Access | 10 |  | 2015-04-10 | 38.46%
29 | Regulations Access | 10 |  | 2015-04-10 | 40%
38 | Membership Manager Contract | 5 |  | 2015-04-10 | 40.77%
41 | Regression Test Harness Design | 5 |  | 2015-04-10 | 41.54%
22 | Data Migration | 10 |  | 2015-04-17 | 43.08%
39 | Market Manager Contract | 5 |  | 2015-04-17 | 43.85%
40 | Education Manager Contract | 5 |  | 2015-04-17 | 44.62%
8 | Test Harness | 25 |  | 2015-05-01 | 48.46%
28 | Workflows Access | 20 |  | 2015-05-01 | 51.54%
10 | UI Design | 20 |  | 2015-05-08 | 54.62%
42 | Membership Manager Simulator | 15 |  | 2015-05-08 | 56.92%
43 | Market Manager Simulator | 15 |  | 2015-05-08 | 59.23%
44 | Education Manager Simulator | 15 |  | 2015-05-08 | 61.54%
30 | Regulations Engine A | 30 |  | 2015-05-22 | 66.15%
45 | Members Portal | 15 |  | 2015-05-29 | 68.46%
11 | Manual | 20 |  | 2015-06-05 | 71.54%
32 | Regulations Engine B | 15 |  | 2015-06-12 | 73.85%
33 | Abstract Manager | 30 |  | 2015-06-12 | 78.46%
48 | Marketplace App | 25 |  | 2015-06-12 | 82.31%
46 | Contractors Portal | 15 |  | 2015-06-19 | 84.62%
34 | Membership Manager | 10 |  | 2015-06-26 | 86.15%
36 | Education Manager | 10 |  | 2015-06-26 | 87.69%
37 | Regression Test Harness | 10 |  | 2015-06-26 | 89.23%
47 | Education Portal | 10 |  | 2015-06-26 | 90.77%
35 | Market Manager | 10 |  | 2015-07-03 | 92.31%
49 | Members Portal Integration | 5 |  | 2015-07-03 | 93.08%
51 | Education Portal Integration | 5 |  | 2015-07-03 | 93.85%
52 | Apps Integration | 5 |  | 2015-07-03 | 94.62%
50 | Contractors Portal Integration | 5 |  | 2015-07-10 | 95.38%
53 | Manual Polishing | 10 |  | 2015-07-10 | 96.92%
54 | System Testing | 10 |  | 2015-07-24 | 98.46%
55 | System Rollout | 10 | 5,19,20 | 2015-08-07 | 100%
| Total Planned Effort | 650
| Duration | 7.1333

## Staffing
Date | Project Manager | Product Manager | Architect | Developers | DevOps | Test Engineers/UX | Testers | Cost (M/M) | Direct Cost
Start
2015-01-05 | 1 | 1 | 1 |  |  |  |  | 0 | 0
2015-01-23 | 1 | 1 | 1 |  |  |  |  | 1.8 | 1.2
2015-01-26 | 1 | 1 | 1 |  |  |  |  | 0.3 | 0.3
2015-02-06 | 1 | 1 | 1 |  |  |  |  | 1.1 | 1.1
2015-02-09 | 1 | 1 | 1 |  |  |  |  | 0.3 | 0.3
2015-02-13 | 1 | 1 | 1 |  |  |  |  | 0.4 | 0.4
2015-02-16 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.4 | 3
2015-02-20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.93333 | 0.53333 | 4
2015-02-23 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 0.7 | 9
2015-02-27 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1.3333 | 0.93333 | 12
2015-03-02 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 0.6 | 12
2015-03-06 | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 1.3333 | 0.8 | 16
2015-03-09 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 1.1 | 0.7 | 15
2015-03-13 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 1.4667 | 0.93333 | 20
2015-03-16 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 1.1 | 0.7 | 15
2015-03-20 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 1.4667 | 0.93333 | 20
2015-03-23 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1.2 | 0.8 | 18
2015-03-27 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1.6 | 1.0667 | 24
2015-03-30 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1.2 | 0.8 | 18
2015-04-03 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1.6 | 1.0667 | 24
2015-04-06 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1.2 | 0.8 | 18
2015-04-10 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1.6 | 1.0667 | 24
2015-04-13 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1.2 | 0.8 | 18
2015-04-17 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1.6 | 1.0667 | 24
2015-04-20 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 1.1 | 0.7 | 15
2015-05-01 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 4.0333 | 2.5667 | 55
2015-05-04 | 1 | 1 | 1 | 5 | 1 |  | 1 | 1 | 0.6 | 15
2015-05-08 | 1 | 1 | 1 | 5 | 1 |  | 1 | 1.3333 | 0.8 | 20
2015-05-11 | 1 | 1 | 1 | 5 | 1 |  | 1 | 1 | 0.7 | 15
2015-05-22 | 1 | 1 | 1 | 5 | 1 |  | 1 | 3.6667 | 2.5667 | 55
2015-05-25 | 1 | 1 | 1 | 5 | 1 |  | 1 | 1 | 0.6 | 15
2015-05-29 | 1 | 1 | 1 | 5 | 1 |  | 1 | 1.3333 | 0.8 | 20
2015-06-01 | 1 | 1 | 1 | 5 | 1 |  | 1 | 1 | 0.6 | 15
2015-06-05 | 1 | 1 | 1 | 5 | 1 |  | 1 | 1.3333 | 0.8 | 20
2015-06-12 | 1 | 1 | 1 | 5 | 1 |  | 1 | 2.3333 | 1.1667 | 35
2015-06-15 | 1 | 1 | 1 | 5 | 1 |  | 1 | 1 | 0.5 | 15
2015-06-19 | 1 | 1 | 1 | 5 | 1 |  | 1 | 1.3333 | 0.66667 | 20
2015-06-22 | 1 | 1 | 1 | 5 | 1 |  | 1 | 1 | 0.5 | 15
2015-06-26 | 1 | 1 | 1 | 5 | 1 |  | 1 | 1.3333 | 0.66667 | 20
2015-06-29 | 1 | 1 | 1 | 4 | 1 |  | 1 | 0.9 | 0.5 | 12
2015-07-03 | 1 | 1 | 1 | 4 | 1 |  | 1 | 1.2 | 0.66667 | 16
2015-07-06 | 1 | 1 | 1 | 1 | 1 |  | 1 | 0.6 | 0.2 | 3
2015-07-10 | 1 | 1 | 1 | 1 | 1 |  | 1 | 0.8 | 0.26667 | 4 | Average Devs: | 4.7153
2015-07-13 | 1 | 1 | 1 |  | 1 |  | 2 | 0.6 | 0.2 |  | Average Staff: | 8.2009 | 68.34%
2015-07-24 | 1 | 1 | 1 |  | 1 |  | 2 | 2.2 | 0.73333
2015-07-27 | 1 | 1 | 1 |  | 1 |  |  | 0.4 | 0.4
2015-08-07 | 1 | 1 | 1 |  | 1 |  |  | 1.4667 | 1.4667
[7 empty] | Total | 58.5 | 36.6667

## Summary
Overall
Cost in man months | 58.5
Duration in months | 7.1333
Average staffing | 8.2009
Efficiency | 37.04%
Front End | 18.22%

## Complexity
ID | Activity | Depends on | Reduced Dependencies | Number of Dependencies Per Acticity
1 | Start |  |  |  | P |  | 1
2 | Requirements | 1 | 1 | 1 | N | Number of Activities | 58
3 | Architecture | 1 | 1 | 1 | E | Total Dependencies | 93
4 | Project Planning | 3 | 3 | 1
5 | Management Education | 4 | 4 | 1 | C | Complexity | 37
6 | SDP Review | 5,3,2 | 5,2 | 2
7 | UX Design | 6 | 6 | 1
8 | Dev Training | 6 | 6 | 1
9 | Test Plan | 8 | 8 | 1
10 | Test Harness | 9 | 9 | 1
11 | Build and Setup | 6 | 6 | 1
12 | UI Design | 7,32 | 7,32 | 2
13 | Manual | 12 | 12 | 1
14 | Logging | 8 | 8 | 1
15 | Message Bus | 8 | 8 | 1
16 | Security | 8,14 | 14 | 1
17 | Infrastructure Complete | 16,15,14,11 | 16,15,11 | 3
18 | Payments DB | 20 | 20 | 1
19 | Members DB | 6 | 6 | 1
20 | Projects DB | 21 | 21 | 1
21 | Contractors DB | 19 | 19 | 1
22 | Education DB | 18 | 18 | 1
23 | Workflows Repository | 15 | 15 | 1
24 | Regulations DB | 22 | 22 | 1
25 | Data Migration | 18,19,20,21,22,23,24 | 23,24 | 2
26 | Payments Access | 18,34 | 18,34 | 2
27 | Members Access | 19 | 19 | 1
28 | Projects Access | 20,29 | 20,29 | 2
29 | Contractors Access | 21 | 21 | 1
30 | Education Access | 22 | 22 | 1
31 | Workflows Access | 23 | 23 | 1
32 | Regulations Access | 24,27 | 24,27 | 2
33 | Regulations Engine A | 32 | 32 | 1
34 | Search Engine | 27 | 27 | 1
35 | Regulations Engine B | 28,29,33 | 28,33 | 2
36 | Abstract Manager | 31,17 | 31,17 | 2
37 | Membership Manager | 36,27,26,33,41 | 36,26,33,41 | 4
38 | Market Manager | 36,28,34,35,49,42 | 36,35,49 | 3
39 | Education Manager | 36,30,43 | 36,30,43 | 3
40 | Regression Test Harness | 36,44 | 36,44 | 2
41 | Membership Manager Contract | 17 | 17 | 1
42 | Market Manager Contract | 17,41 | 41 | 1
43 | Education Manager Contract | 17,26 | 17,26 | 2
44 | Regression Test Harness Design | 17 | 17 | 1
45 | Membership Manager Simulator | 41,43 | 41,43 | 2
46 | Market Manager Simulator | 42 | 42 | 1
47 | Education Manager Simulator | 43 | 43 | 1
48 | Members Portal | 12,45 | 12,45 | 2
49 | Contractors Portal | 12,46,48 | 46,48 | 2
50 | Education Portal | 12,47,51 | 51 | 1
51 | Marketplace App | 12,45,46,47 | 12,45,46,47 | 4
52 | Members Portal Integration | 48,37 | 48,37 | 2
53 | Contractors Portal Integration | 49,38 | 38 | 1
54 | Education Portal Integration | 50,39 | 50,39 | 2
55 | Marketplace Apps Integration | 51,40,50 | 40,50 | 2
56 | Manual Polishing | 48,49,50,51 | 49,50 | 2
57 | System Testing | 10,52,53,54,55 | 10,52,53,54,55 | 5
58 | System Rollout | 25,13,57,56 | 25,13,57,56 | 4