## Project Plan
ID | Activity | Duration | Depends on | Planned Completion Date | Planned Earned Value
| Start | 0 |  | 2015-01-05 | 0%
1 | Requirements | 15 |  | 2015-01-23 | 2.655%
2 | Architecture | 15 |  | 2015-01-23 | 5.31%
3 | Project Planning | 10 |  | 2015-02-06 | 7.08%
4 | Management Education | 5 |  | 2015-02-13 | 7.965%
5 | SDP Review | 0 |  | 2015-02-13 | 7.965%
7 | Dev Training | 5 |  | 2015-02-20 | 8.85%
10 | Build and Setup | 10 |  | 2015-02-27 | 10.62%
13 | Logging | 10 |  | 2015-03-06 | 12.39%
14 | Message Bus | 15 |  | 2015-03-13 | 15.04%
15 | Security | 20 |  | 2015-03-20 | 18.58%
16 | Infrastructure Done | 0 |  | 2015-03-20 | 18.58%
8 | Test Plan | 25 |  | 2015-03-27 | 23.01%
23 | Regulations DB | 5 |  | 2015-03-27 | 23.89%
6 | UX Design | 10 |  | 2015-04-03 | 25.66%
18 | Members DB | 5 |  | 2015-04-03 | 26.55%
22 | Workflows Repository | 15 |  | 2015-04-03 | 29.2%
19 | Projects DB | 5 |  | 2015-04-10 | 30.09%
31 | Regulations Access | 10 |  | 2015-04-10 | 31.86%
20 | Contractors DB | 5 |  | 2015-04-17 | 32.74%
26 | Members Access | 10 |  | 2015-04-17 | 34.51%
21 | Education DB | 5 |  | 2015-04-24 | 35.4%
27 | Projects Access | 10 |  | 2015-04-24 | 37.17%
9 | Test Harness | 25 |  | 2015-05-01 | 41.59%
11 | UI Design | 20 |  | 2015-05-01 | 45.13%
17 | Payments DB | 5 |  | 2015-05-01 | 46.02%
28 | Contractors Access | 10 |  | 2015-05-01 | 47.79%
30 | Workflows Access | 20 |  | 2015-05-01 | 51.33%
24 | Data Migration | 10 |  | 2015-05-15 | 53.1%
25 | Payments Access | 10 |  | 2015-05-15 | 54.87%
33 | Search Engine | 15 |  | 2015-05-15 | 57.52%
32 | Regulations Engine A | 30 |  | 2015-05-22 | 62.83%
12 | Manual | 20 |  | 2015-05-29 | 66.37%
29 | Education Access | 10 |  | 2015-05-29 | 68.14%
34 | Regulations Engine B | 15 |  | 2015-06-12 | 70.8%
35 | Abstract Manager | 30 |  | 2015-06-12 | 76.11%
36 | Membership Manager | 10 |  | 2015-06-26 | 77.88%
37 | Market Manager | 10 |  | 2015-06-26 | 79.65%
38 | Education Manager | 10 |  | 2015-06-26 | 81.42%
39 | Regression Test Harness | 10 |  | 2015-06-26 | 83.19%
40 | Managers Complete | 0 |  | 2015-06-26 | 83.19%
43 | Education Portal | 10 |  | 2015-07-10 | 84.96%
41 | Members Portal | 15 |  | 2015-07-17 | 87.61%
42 | Contractors Portal | 15 |  | 2015-07-17 | 90.27%
44 | Marketplace App | 25 |  | 2015-07-31 | 94.69%
45 | Manual Polishing | 10 |  | 2015-08-14 | 96.46%
46 | System Testing | 10 |  | 2015-08-14 | 98.23%
47 | System Rollout | 10 |  | 2015-08-28 | 100%
| Total Planned Effort | 565
| Duration | 7.8333

## Staffing
Date | Project Manager | Product Manager | Architect | Developers | DevOps | Test Engineers/UX | Testers | Cost (M/M) | Direct Cost
Start
2015-01-05 | 1 | 1 | 1 |  |  |  |  | 0 | 0
2015-01-23 | 1 | 1 | 1 |  |  |  |  | 1.8 | 1.2
2015-01-26 | 1 | 1 | 1 |  |  |  |  | 0.3 | 0.3
2015-02-06 | 1 | 1 | 1 |  |  |  |  | 1.1 | 1.1
2015-02-09 | 1 | 1 | 1 |  |  |  |  | 0.3 | 0.3
2015-02-13 | 1 | 1 | 1 |  |  |  |  | 0.4 | 0.4
2015-02-16 | 1 | 1 | 1 |  | 1 |  | 1 | 0.5 | 0.2
2015-02-20 | 1 | 1 | 1 |  | 1 |  | 1 | 0.66667 | 0.26667
2015-02-23 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0.8 | 0.5 | 6
2015-02-27 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.0667 | 0.66667 | 8
2015-03-06 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.8667 | 0.93333 | 14
2015-03-13 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.8667 | 0.93333 | 14
2015-03-16 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0.8 | 0.4 | 6
2015-03-20 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1.0667 | 0.53333 | 8
2015-03-23 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 0.6 | 9
2015-03-27 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1.3333 | 0.8 | 12
2015-03-30 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 0.6 | 9
2015-04-03 | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1.3333 | 0.8 | 12
2015-04-06 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1.1 | 0.6 | 12
2015-04-10 | 1 | 1 | 1 | 4 | 1 | 2 | 1 | 1.4667 | 0.8 | 16
2015-04-13 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 1.2 | 0.7 | 15
2015-04-17 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 1.6 | 0.93333 | 20
2015-04-20 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 1.2 | 0.7 | 15
2015-04-24 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 1.6 | 0.93333 | 20
2015-04-27 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 1.2 | 0.7 | 15
2015-05-01 | 1 | 1 | 1 | 5 | 1 | 2 | 1 | 1.6 | 0.93333 | 20
2015-05-04 | 1 | 1 | 1 | 5 | 1 |  | 1 | 1 | 0.6 | 15
2015-05-15 | 1 | 1 | 1 | 5 | 1 |  | 1 | 3.6667 | 2.2 | 55
2015-05-18 | 1 | 1 | 1 | 4 | 1 |  | 1 | 0.9 | 0.5 | 12
2015-05-22 | 1 | 1 | 1 | 4 | 1 |  | 1 | 1.2 | 0.66667 | 16
2015-05-25 | 1 | 1 | 1 | 4 | 1 |  | 1 | 0.9 | 0.5 | 12
2015-05-29 | 1 | 1 | 1 | 4 | 1 |  | 1 | 1.2 | 0.66667 | 16
2015-06-12 | 1 | 1 | 1 | 4 | 1 |  | 1 | 4.2 | 1.8667 | 56
2015-06-15 | 1 | 1 | 1 | 4 | 1 |  | 1 | 0.9 | 0.4 | 12
2015-06-26 | 1 | 1 | 1 | 4 | 1 |  | 1 | 3.3 | 1.4667 | 44
2015-06-29 | 1 | 1 | 1 | 4 | 1 |  | 1 | 0.9 | 0.4 | 12
2015-07-10 | 1 | 1 | 1 | 4 | 1 |  | 1 | 3.3 | 1.4667 | 44
2015-07-17 | 1 | 1 | 1 | 3 | 1 |  | 1 | 1.8667 | 0.7 | 21
2015-07-31 | 1 | 1 | 1 | 1 | 1 |  | 1 | 2.8 | 0.46667 | 14 | Average Devs: | 3.5443
2015-08-03 | 1 | 1 | 1 |  | 1 |  | 2 | 0.6 | 0.3 |  | Average Staff: | 7.5277 | 62.73%
2015-08-14 | 1 | 1 | 1 |  | 1 |  | 2 | 2.2 | 1.1
2015-08-17 | 1 | 1 | 1 |  | 1 |  |  | 0.4 | 0.4
2015-08-28 | 1 | 1 | 1 |  | 1 |  |  | 1.4667 | 1.4667
[7 empty] | Total | 58.9667 | 32

## Summary
Overall
Cost in man months | 58.9667
Duration in months | 7.8333
Average staffing | 7.5277
Efficiency | 31.94%
Front End | 16.6%

## Complexity
ID | Activity | Depends on | Reduced Dependencies | Number of Dependencies Per Acticity
1 | Start |  |  |  | P |  | 1
2 | Requirements | 1 | 1 | 1 | N | Number of Activities | 49
3 | Architecture | 1 | 1 | 1 | E | Total Dependencies | 80
4 | Project Planning | 3 | 3 | 1
5 | Management Education | 4 | 4 | 1 | C | Complexity | 33
6 | SDP Review | 5,2 | 5,2 | 2
7 | UX Design | 17 | 17 | 1
8 | Dev Training | 6 | 6 | 1
9 | Test Plan | 8 | 8 | 1
10 | Test Harness | 9 | 9 | 1
11 | Build and Setup | 6 | 6 | 1
12 | UI Design | 7 | 7 | 1
13 | Manual | 12 | 12 | 1
14 | Logging | 8 | 8 | 1
15 | Message Bus | 8 | 8 | 1
16 | Security | 8 | 8 | 1
17 | Infrastructure Complete | 16,15,14,11 | 16,15,14,11 | 4
18 | Payments DB | 17,22 | 22 | 1
19 | Members DB | 17,24 | 24 | 1
20 | Projects DB | 17,19 | 19 | 1
21 | Contractors DB | 17,20 | 20 | 1
22 | Education DB | 17,21 | 21 | 1
23 | Workflows Repository | 15 | 15 | 1
24 | Regulations DB | 17 | 17 | 1
25 | Data Migration | 18,19,20,21,22,24 | 18 | 1
26 | Payments Access | 18 | 18 | 1
27 | Members Access | 19 | 19 | 1
28 | Projects Access | 20 | 20 | 1
29 | Contractors Access | 21 | 21 | 1
30 | Education Access | 22,34 | 22,34 | 2
31 | Workflows Access | 23 | 23 | 1
32 | Regulations Access | 24 | 24 | 1
33 | Regulations Engine A | 32 | 32 | 1
34 | Search Engine | 27,28 | 27,28 | 2
35 | Regulations Engine B | 28,29,33 | 28,29,33 | 3
36 | Abstract Manager | 31,17 | 31,17 | 2
37 | Membership Manager | 36,27,26,33 | 36,27,26,33 | 4
38 | Market Manager | 36,28,34,35 | 36,34,35 | 3
39 | Education Manager | 36,30 | 36,30 | 2
40 | Regression Test Harness | 36 | 36 | 1
41 | Managers Complete | 37,38,39,40 | 37,38,39,40 | 4
42 | Members Portal | 12,41 | 12,41 | 2
43 | Contractors Portal | 12,41 | 12,41 | 2
44 | Education Portal | 12,41 | 12,41 | 2
45 | Marketplace App | 12,41 | 12,41 | 2
46 | Manual Polishing | 42,43,44,45 | 42,43,44,45 | 4
47 | System Testing | 10,42,43,44,45 | 10,42,43,44,45 | 5
48 | System Rollout | 25,13,47,46 | 25,13,47,46 | 4
49 | End | 48 | 48 | 1