## Instructions
Przegląd
Ten zestaw ćwiczeń zawiera wiele opcji szablonów do zarządzania zarówno rejestrem produktu, jak i rejestrem sprintu. Wybierz preferowane szablony - wybierz jeden szablon rejestru produktu (opcja 1, 2 lub 3) i jeden szablon rejestru sprintu (1-tygodniowy lub 2-tygodniowy) - a następnie usuń pozostałe. Poniżej znajdują się instrukcje dotyczące korzystania z każdego szablonu, w tym pola, które można edytować, a które nie, oraz kwestie, na które należy zwrócić uwagę podczas wprowadzania modyfikacji.
Instrukcje dotyczące rejestru produktu
Uwaga: Każdy z trzech szablonów rejestru produktu wykorzystuje formatowanie warunkowe zamiast programowania Visual Basic (VBA), aby uniknąć korzystania z makr. Makra mogą być problematyczne dla niektórych użytkowników w niektórych środowiskach bezpieczeństwa. Opcje szablonu rejestru produktu zapewniają dane i obliczenia umożliwiające nie tylko wygenerowanie wykresu spalania projektu/wydania, ale także zapewnienie empirycznych ekstrapolacji „PERT” dla dat wydania w oparciu o prędkość zespołu scrumowego. Trzy opcje szablonów są identyczne, przy następujących różnicach (przewidzianych pod kątem indywidualnych preferencji): Rejestr produktu - opcja 1: Ta opcja wyróżnia wszystkie wiersze w zakresach obliczonych w kolumnach K, L i M. Rejestr produktu - opcja 2: Ta opcja podświetla tylko ostatni wiersz zakresów obliczonych w kolumnach K, L i M. Rejestr produktu - opcja 3: Ta opcja podkreśla tylko ostatni wiersz zakresów obliczonych w kolumnach K, L i M. Dane ekstrapolacji są obliczane w zakresie F2:M15 i zakładają projekt obejmujący 10 sprintów. Można to zmodyfikować, ale należy pamiętać, że zakres danych wykresu spalania musi zostać ręcznie zaktualizowany, aby dopasować go do wszelkich zmian. „P” oznacza „pesymistyczny” (tj. najniższa prędkość), „ML” oznacza „najbardziej prawdopodobny” (tj. średnia prędkość), a „O” oznacza „optymistyczny” (tj. najwyższa prędkość). Należy pamiętać, że wiele komórek zawiera wartości i/lub formuły wymagane do obliczenia innych komórek i/lub wykresu spalania. Komentarze są podawane w każdej komórce (lub pierwszej komórce w zakresie), która wymaga ręcznej aktualizacji przez użytkownika. Unikaj zmiany wartości w komórkach, które nie mają czerwonej flagi w prawym górnym rogu, wskazującej na komentarz.
Instrukcje dotyczące rejestru sprintu
Szablon rejestru sprintu dla opcji 1- i 2-tygodniowych zawiera dane i obliczenia umożliwiające wygenerowanie wykresu wypalenia sprintu zarówno dla punktów historyjek, jak i godzin zadań. Instrukcje można znaleźć na stronie https://platinumedge.com/blog/anatomy-sprint-backlog. Obie opcje szablonu są identyczne, z wyjątkiem długości sprintu. Dane wykresu spalania są generowane na podstawie danych w wierszach 81-84. Wiersze można usuwać lub dodawać, aby pomieścić więcej lub mniej historyjek użytkownika i/lub zadań w każdej historyjce użytkownika, jednak należy pamiętać, że formuły mogą wymagać aktualizacji w tych wierszach, a także w każdym wierszu historyjki użytkownika. Należy pamiętać, że wiele komórek zawiera wartości i/lub formuły wymagane do obliczenia innych komórek i/lub wykresu spalania. Unikaj zmiany wartości w komórkach zawierających formuły. Można również zauważyć, że kształt linii punktów historyjek różni się nieco w zależności od długości sprintu. Wersja 1-tygodniowa to normalny kształt schodów, jakiego można się spodziewać. Wersja 2-tygodniowa ma lekkie, ale zauważalne nachylenie zamiast prostego pionowego spadku. Wynika to z logiki programu Excel używanej do ukrywania dni weekendowych, w których nie będą wykonywane żadne prace deweloperskie. Jest to niewielka różnica wizualna, która nie powinna negatywnie wpływać na użyteczność widoczności postępów w sprincie.

## Rejestr produku - opcja 1
<Nazwa produktu> Prognozy wydania |  |  | Requirement |  | Empiryczne obliczenia PERT |  |  |  |  | Zakres P | Zakres ML | Zakres O
|  |  | Improvement |  |  | Dane rzeczywiste | Sprinty | Dane rzeczywiste | Plan | Pozostało | Pozostało | Pozostało
2016-10-27 | Rozpoczęcie projektu |  | Maintenance |  | Sprint | Szybkość | Pozostało | Spalanie | Spalanie | 10 | 10 | 10
7 | Długość sprintu (dni) |  | Overhead |  | Start | 10 | 10 | 142 | 142 | 100 | 100 | 100
3 | Sprinty wydania 1 (#) |  |  |  | 1 |  | 9 | 142 | 127.8 | 90 | 90 | 90
7 | Długość sprintów wydania 1 (dni) |  |  |  | 2 |  | 8 | 142 | 113.6 | 80 | 80 | 80
2016-11-24 | Data wydania 1 |  |  |  | 3 |  | 7 | 142 | 99.4 | 70 | 70 | 70
2 | Sprinty wydania 2 (#) |  |  |  | 4 |  | 6 | 142 | 85.2 | 60 | 60 | 60
0 | Długość sprintów wydania 2 (dni) |  |  |  | 5 |  | 5 | 142 | 71 | 50 | 50 | 50
2016-12-08 | Data wydania 2 |  |  |  | 6 |  | 4 | 142 | 56.8 | 40 | 40 | 40
3 | Sprinty wydania 3 (#) |  |  |  | 7 |  | 3 | 142 | 42.6 | 30 | 30 | 30
0 | Długość sprintów wydania 3 (dni) |  |  |  | 8 |  | 2 | 142 | 28.4 | 20 | 20 | 20
2016-12-29 | Data wydania 3 |  |  |  | 9 |  | 1 | 142 | 14.2 | 10 | 10 | 10
[5 empty] | 10 |  | 0 | 142 | 0 | 0 | 0 | 0
<Nazwa produktu> Rejestr produktu | [5 empty] | Bieżące | Sprint | Wydanie | Wydanie
ID | Nazwa | Opis | Kryteria akceptacji | Typ | Rozmiar | Łącznie | Ukończone | Daty | Cele
2 | <Nazwa elementu rejestru produktu> | Jako ____ chcę ____, więc ____. | Kiedy to robię: ____, dzieje się to: ____. | Requirement | 2 | 2
3 | <Nazwa elementu rejestru produktu> |  |  |  | 1 | 3
4 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 6
5 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 9
1 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 14
6 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 17
7 | <Nazwa elementu rejestru produktu> |  |  |  | 2 | 19
8 | <Nazwa elementu rejestru produktu> |  |  |  | 8 | 27
9 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 32
10 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 35
11 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 38 |  | 2016-11-24 | Wydanie 1: <cel>
13 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 43
15 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 48
14 | <Nazwa elementu rejestru produktu> |  |  |  | 8 | 56
16 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 61
20 | <Nazwa elementu rejestru produktu> |  |  |  | 13 | 74 |  | 2016-12-08 | Wydanie 2: <cel>
19 | <Nazwa elementu rejestru produktu> |  |  |  | 13 | 87
17 | <Nazwa elementu rejestru produktu> |  |  |  | 21 | 108
18 | <Nazwa elementu rejestru produktu> |  |  |  | 34 | 142 |  | 2016-12-29 | Wydanie 3: <cel>
22 | <Nazwa elementu rejestru produktu> |  |  |  | 34 | 176
24 | <Nazwa elementu rejestru produktu> |  |  |  | 21 | 197
25 | <Nazwa elementu rejestru produktu> |  |  |  | 34 | 231
26 | <Nazwa elementu rejestru produktu> |  |  |  | 13 | 244
27 | <Nazwa elementu rejestru produktu> |  |  |  | 55 | 299
28 | <Nazwa elementu rejestru produktu> |  |  |  | 89 | 388
29 | <Nazwa elementu rejestru produktu> |  |  |  | 55 | 443
30 | <Nazwa elementu rejestru produktu> |  |  |  | 34 | 477
31 | <Nazwa elementu rejestru produktu> |  |  |  | 55 | 532
32 | <Nazwa elementu rejestru produktu> |  |  |  | 21 | 553
34 | <Nazwa elementu rejestru produktu> |  |  |  | 13 | 566
35 | <Nazwa elementu rejestru produktu> |  |  |  | 55 | 621
36 | <Nazwa elementu rejestru produktu> |  |  |  | 144 | 765
Note on A2: Instructions: Update the portion in <> with your product's name.
Note on A4: Instructions (not required): Insert the project start date.
Note on A5: Instructions (not required): Enter the sprint length, in multiples of 7 days per week of sprint.
Note on G5: Instructions: Enter the scrum team's conservative estimate of how many story points they think they can accomplish the first sprint. This cell will be ignored as soon as there is actual velocity data from the first sprint.
Note on I5: Instructions: If the product owner has a target point in the product backlog, update this cell to point to the cell in column G of the last backlog item included in the scope of the project. (This template provides an example of how you would point to PBI 0018, if that were the target.)
Note on A6: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A7: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A9: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A10: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A12: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A13: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A18: Instructions: Update the portion in <> with your product's name.
Note on A19: Instructions: Enter the ID of the product backlog item (PBI). The ID usually reflects when it was entered in the system, not the priority. The order of the PBIs indicates the priority. This applies to all cells in this column.
Note on B19: Instructions: Enter the title of the product backlog item. Applies to all cells in this column.
Note on C19: Instructions: Enter the product backlog item description. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on D19: Instructions: Enter the product backlog item acceptance criteria. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on E19: Instructions: Select what type of product backlog item this is (Applies to all cells in this column): Requirement: Typically a user story--work that needs to be done to generate functionality for the user. Improvement: Action items from the sprint retrospective. Maintenance: Development work that neesd to be done on the system, but doesn't create new functionality.. Overhead: Non-development work that needs to be done, but doesn't add direct value to the user.
Note on F19: Instructions: Enter the Fibonacci size estimate assigned by the development team. Applies to all cells in this column.
Note on H19: Instructions: Enter the number of the sprint when the PBI was completed (done).Enter whole numbers to match the format of what appears in F6:F15 above. Applies to all cells in this column.
Note on I19: Instructions (optional): Update any cell below to point to the date generated in A4:A14 indicating the projected release date. Note: This may change as velocity changes.
Note on J19: Instructions (optional): Update <> with the actual release goal.

## Rejestr produktu - opcja 2
<Nazwa produktu> Prognozy wydania |  |  | Requirement |  | Empiryczne obliczenia PERT |  |  |  |  | Zakres P | Zakres ML | Zakres O
|  |  | Improvement |  |  | Dane rzeczywiste | Sprinty | Cel | Plan | Pozostało | Pozostało | Pozostało
2016-10-27 | Rozpoczęcie projektu |  | Maintenance |  | Sprint | Szybkość | Pozostało | Spalanie | Spalanie | 10 | 10 | 10
7 | Długość sprintu (dni) |  | Overhead |  | Start | 10 | 10 | 142 | 142 | 100 | 100 | 100
3 | Sprinty wydania 1 (#) |  |  |  | 1 |  | 9 | 142 | 127.8 | 90 | 90 | 90
7 | Długość sprintów wydania 1 (dni) |  |  |  | 2 |  | 8 | 142 | 113.6 | 80 | 80 | 80
2016-11-24 | Data wydania 1 |  |  |  | 3 |  | 7 | 142 | 99.4 | 70 | 70 | 70
2 | Sprinty wydania 2 (#) |  |  |  | 4 |  | 6 | 142 | 85.2 | 60 | 60 | 60
0 | Długość sprintów wydania 2 (dni) |  |  |  | 5 |  | 5 | 142 | 71 | 50 | 50 | 50
2016-12-08 | Data wydania 2 |  |  |  | 6 |  | 4 | 142 | 56.8 | 40 | 40 | 40
3 | Sprinty wydania 3 (#) |  |  |  | 7 |  | 3 | 142 | 42.6 | 30 | 30 | 30
0 | Długość sprintów wydania 3 (dni) |  |  |  | 8 |  | 2 | 142 | 28.4 | 20 | 20 | 20
2016-12-29 | Data wydania 3 |  |  |  | 9 |  | 1 | 142 | 14.2 | 10 | 10 | 10
[5 empty] | 10 |  | 0 | 142 | 0 | 0 | 0 | 0
<Nazwa produktu> Rejestr produktu | [5 empty] | Bieżące | Sprint | Wydanie | Wydanie
ID | Nazwa | Opis | Kryteria akceptacji | Typ | Rozmiar | Łącznie | Ukończone | Daty | Cele
2 | <Nazwa elementu rejestru produktu> | Jako ____ chcę ____, więc ____. | Kiedy to robię: ____, dzieje się to: ____. | Requirement | 2 | 2
3 | <Nazwa elementu rejestru produktu> |  |  |  | 1 | 3
4 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 6
5 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 9
1 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 14
6 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 17
7 | <Nazwa elementu rejestru produktu> |  |  |  | 2 | 19
8 | <Nazwa elementu rejestru produktu> |  |  |  | 8 | 27
9 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 32
10 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 35
11 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 38 |  | 2016-11-24 | Wydanie 1: <cel>
13 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 43
15 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 48
14 | <Nazwa elementu rejestru produktu> |  |  |  | 8 | 56
16 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 61
20 | <Nazwa elementu rejestru produktu> |  |  |  | 13 | 74 |  | 2016-12-08 | Wydanie 2: <cel>
19 | <Nazwa elementu rejestru produktu> |  |  |  | 13 | 87
17 | <Nazwa elementu rejestru produktu> |  |  |  | 21 | 108
18 | <Nazwa elementu rejestru produktu> |  |  |  | 34 | 142 |  | 2016-12-29 | Wydanie 3: <cel>
22 | <Nazwa elementu rejestru produktu> |  |  |  | 34 | 176
24 | <Nazwa elementu rejestru produktu> |  |  |  | 21 | 197
25 | <Nazwa elementu rejestru produktu> |  |  |  | 34 | 231
26 | <Nazwa elementu rejestru produktu> |  |  |  | 13 | 244
27 | <Nazwa elementu rejestru produktu> |  |  |  | 55 | 299
28 | <Nazwa elementu rejestru produktu> |  |  |  | 89 | 388
29 | <Nazwa elementu rejestru produktu> |  |  |  | 55 | 443
30 | <Nazwa elementu rejestru produktu> |  |  |  | 34 | 477
31 | <Nazwa elementu rejestru produktu> |  |  |  | 55 | 532
32 | <Nazwa elementu rejestru produktu> |  |  |  | 21 | 553
34 | <Nazwa elementu rejestru produktu> |  |  |  | 13 | 566
35 | <Nazwa elementu rejestru produktu> |  |  |  | 55 | 621
36 | <Nazwa elementu rejestru produktu> |  |  |  | 144 | 765
765
Note on A2: Instructions: Update the portion in <> with your product's name.
Note on A4: Instructions (not required): Insert the project start date.
Note on A5: Instructions (not required): Enter the sprint length, in multiples of 7 days per week of sprint.
Note on G5: Instructions: Enter the scrum team's conservative estimate of how many story points they think they can accomplish the first sprint. This cell will be ignored as soon as there is actual velocity data from the first sprint.
Note on I5: Instructions: If the product owner has a target point in the product backlog, update this cell to point to the cell in column G of the last backlog item included in the scope of the project. (This template provides an example of how you would point to PBI 0018, if that were the target.)
Note on A6: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A7: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A9: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A10: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A12: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A13: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A18: Instructions: Update the portion in <> with your product's name.
Note on A19: Instructions: Enter the ID of the product backlog item (PBI). The ID usually reflects when it was entered in the system, not the priority. The order of the PBIs indicates the priority. This applies to all cells in this column.
Note on B19: Instructions: Enter the title of the product backlog item. Applies to all cells in this column.
Note on C19: Instructions: Enter the product backlog item description. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on D19: Instructions: Enter the product backlog item acceptance criteria. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on E19: Instructions: Select what type of product backlog item this is (Applies to all cells in this column): Requirement: Typically a user story--work that needs to be done to generate functionality for the user. Improvement: Action items from the sprint retrospective. Maintenance: Development work that neesd to be done on the system, but doesn't create new functionality.. Overhead: Non-development work that needs to be done, but doesn't add direct value to the user.
Note on F19: Instructions: Enter the Fibonacci size estimate assigned by the development team. Applies to all cells in this column.
Note on H19: Instructions: Enter the number of the sprint when the PBI was completed (done).Enter whole numbers to match the format of what appears in F6:F15 above. Applies to all cells in this column.
Note on I19: Instructions (optional): Update any cell below to point to the date generated in A4:A14 indicating the projected release date. Note: This may change as velocity changes.
Note on J19: Instructions (optional): Update <> with the actual release goal.

## Rejestr produktu - opcja 3
<Nazwa produktu> Prognozy wydania |  |  | Requirement |  | Empiryczne obliczenia PERT |  |  |  |  | Zakres P | Zakres ML | Zakres O
|  |  | Improvement |  |  | Dane rzeczywiste | Sprinty | Cel | Plan | Pozostało | Pozostało | Pozostało
2016-10-27 | Rozpoczęcie projektu |  | Maintenance |  | Sprint | Szybkość | Pozostało | Spalanie | Spalanie | 10 | 10 | 10
7 | Długość sprintu (dni) |  | Overhead |  | Start | 10 | 10 | 142 | 142 | 100 | 100 | 100
3 | Sprinty wydania 1 (#) |  |  |  | 1 |  | 9 | 142 | 127.8 | 90 | 90 | 90
7 | Długość sprintów wydania 1 (dni) |  |  |  | 2 |  | 8 | 142 | 113.6 | 80 | 80 | 80
2016-11-24 | Data wydania 1 |  |  |  | 3 |  | 7 | 142 | 99.4 | 70 | 70 | 70
2 | Sprinty wydania 2 (#) |  |  |  | 4 |  | 6 | 142 | 85.2 | 60 | 60 | 60
0 | Długość sprintów wydania 2 (dni) |  |  |  | 5 |  | 5 | 142 | 71 | 50 | 50 | 50
2016-12-08 | Data wydania 2 |  |  |  | 6 |  | 4 | 142 | 56.8 | 40 | 40 | 40
3 | Sprinty wydania 3 (#) |  |  |  | 7 |  | 3 | 142 | 42.6 | 30 | 30 | 30
0 | Długość sprintów wydania 3 (dni) |  |  |  | 8 |  | 2 | 142 | 28.4 | 20 | 20 | 20
2016-12-29 | Data wydania 3 |  |  |  | 9 |  | 1 | 142 | 14.2 | 10 | 10 | 10
[5 empty] | 10 |  | 0 | 142 | 0 | 0 | 0 | 0
<Nazwa produktu> Rejestr produktu | [5 empty] | Bieżące | Sprint | Wydanie | Wydanie
ID | Nazwa | Opis | Kryteria akceptacji | Typ | Rozmiar | Łącznie | Ukończone | Daty | Cele
2 | <Nazwa elementu rejestru produktu> | Jako ____ chcę ____, więc ____. | Kiedy to robię: ____, dzieje się to: ____. | Requirement | 2 | 2
3 | <Nazwa elementu rejestru produktu> |  |  |  | 1 | 3
4 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 6
5 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 9
1 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 14
6 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 17
7 | <Nazwa elementu rejestru produktu> |  |  |  | 2 | 19
8 | <Nazwa elementu rejestru produktu> |  |  |  | 8 | 27
9 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 32
10 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 35
11 | <Nazwa elementu rejestru produktu> |  |  |  | 3 | 38 |  | 2016-11-24 | Wydanie 1: <cel>
13 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 43
15 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 48
14 | <Nazwa elementu rejestru produktu> |  |  |  | 8 | 56
16 | <Nazwa elementu rejestru produktu> |  |  |  | 5 | 61
20 | <Nazwa elementu rejestru produktu> |  |  |  | 13 | 74 |  | 2016-12-08 | Wydanie 2: <cel>
19 | <Nazwa elementu rejestru produktu> |  |  |  | 13 | 87
17 | <Nazwa elementu rejestru produktu> |  |  |  | 21 | 108
18 | <Nazwa elementu rejestru produktu> |  |  |  | 34 | 142 |  | 2016-12-29 | Wydanie 3: <cel>
22 | <Nazwa elementu rejestru produktu> |  |  |  | 34 | 176
24 | <Nazwa elementu rejestru produktu> |  |  |  | 21 | 197
25 | <Nazwa elementu rejestru produktu> |  |  |  | 34 | 231
26 | <Nazwa elementu rejestru produktu> |  |  |  | 13 | 244
27 | <Nazwa elementu rejestru produktu> |  |  |  | 55 | 299
28 | <Nazwa elementu rejestru produktu> |  |  |  | 89 | 388
29 | <Nazwa elementu rejestru produktu> |  |  |  | 55 | 443
30 | <Nazwa elementu rejestru produktu> |  |  |  | 34 | 477
31 | <Nazwa elementu rejestru produktu> |  |  |  | 55 | 532
32 | <Nazwa elementu rejestru produktu> |  |  |  | 21 | 553
34 | <Nazwa elementu rejestru produktu> |  |  |  | 13 | 566
35 | <Nazwa rejestru produktu> |  |  |  | 55 | 621
36 | <Nazwa rejestru produktu> |  |  |  | 144 | 765
Note on A2: Instructions: Update the portion in <> with your product's name.
Note on A4: Instructions (not required): Insert the project start date.
Note on A5: Instructions (not required): Enter the sprint length, in multiples of 7 days per week of sprint.
Note on G5: Instructions: Enter the scrum team's conservative estimate of how many story points they think they can accomplish the first sprint. This cell will be ignored as soon as there is actual velocity data from the first sprint.
Note on I5: Instructions: If the product owner has a target point in the product backlog, update this cell to point to the cell in column G of the last backlog item included in the scope of the project. (This template provides an example of how you would point to PBI 0018, if that were the target.)
Note on A6: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A7: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A9: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A10: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A12: Instructions (not required): Enter the anticipated number of sprints to achieve the release goal.
Note on A13: Instructions (not required): If you need a release sprint, enter the release sprint length, in multiples of 7 days per week of sprint.
Note on A18: Instructions: Update the portion in <> with your product's name.
Note on A19: Instructions: Enter the ID of the product backlog item (PBI). The ID usually reflects when it was entered in the system, not the priority. The order of the PBIs indicates the priority. This applies to all cells in this column.
Note on B19: Instructions: Enter the title of the product backlog item. Applies to all cells in this column.
Note on C19: Instructions: Enter the product backlog item description. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on D19: Instructions: Enter the product backlog item acceptance criteria. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on E19: Instructions: Select what type of product backlog item this is (Applies to all cells in this column): Requirement: Typically a user story--work that needs to be done to generate functionality for the user. Improvement: Action items from the sprint retrospective. Maintenance: Development work that neesd to be done on the system, but doesn't create new functionality.. Overhead: Non-development work that needs to be done, but doesn't add direct value to the user.
Note on F19: Instructions: Enter the Fibonacci size estimate assigned by the development team. Applies to all cells in this column.
Note on H19: Instructions: Enter the number of the sprint when the PBI was completed (done).Enter whole numbers to match the format of what appears in F6:F15 above. Applies to all cells in this column.
Note on I19: Instructions (optional): Update any cell below to point to the date generated in A4:A14 indicating the projected release date. Note: This may change as velocity changes.
Note on J19: Instructions (optional): Update <> with the actual release goal.

## Rejestr sprintu - 1 tydzień
<Nazwa produktu> - Sprint <#>
Daty sprintów: <Miesiąc> <DD> - <Miesiąc> <DD>, <RRRR>
[6 empty] | Dostępne godziny pracy w sprincie | [6 empty] | Dni w sprincie: |  | 4.5
Cel sprintu | [6 empty] | Pon. | Tu | Wt. | W | Śr. | Th | Czw. | F | Ptk. | Łącznie
Zademonstruj umiejętność w zakresie <celu sprintu>. (UWAGA: Zdefiniuj cel sprintu pod względem działającej funkcjonalności klienta, którą będziesz w stanie zademonstrować wewnętrznym interesariuszom i ewentualnie wypuścić na rynek) | [5 empty] | Deweloperzy | 2018-12-24 | 2018-12-25 | 2018-12-25 | 2018-12-26 | 2018-12-26 | 2018-12-27 | 2018-12-27 | 2018-12-28 | 2018-12-28
[6 empty] | <Deweloper> | 2018-12-24: 4; 2018-12-25: 6; 2018-12-26: 6; 2018-12-27: 6; 2018-12-28: 4 | 26
[6 empty] | <Deweloper> | 2018-12-24: 4; 2018-12-25: 6; 2018-12-26: 6; 2018-12-27: 6; 2018-12-28: 4 | 26
[6 empty] | <Deweloper> | 2018-12-24: 4; 2018-12-25: 6; 2018-12-26: 6; 2018-12-27: 6; 2018-12-28: 4 | 26
[6 empty] | <Deweloper> | 2018-12-24: 4; 2018-12-25: 6; 2018-12-26: 6; 2018-12-27: 6; 2018-12-28: 4 | 26
[6 empty] | <Deweloper> | 2018-12-24: 4; 2018-12-25: 6; 2018-12-26: 6; 2018-12-27: 6; 2018-12-28: 4 | 26
[7 empty] | 2018-12-28: Godziny sprintu łącznie: | 130
[7 empty] | 2018-12-28: Łącznie na dzień: | 28.8889
Wykres spalania funkcji - na podstawie szacowanej liczby pozostałych godzin
[7 empty] | Pon. | Tu | Wt. | W | Śr. | Th | Czw. | F | Ptk.
ID | Zadanie | Opis | Kryteria akceptacji | Typ | Punkty historyjek | Osoba odpowiedzialna | 2018-12-24 | 2018-12-25 | 2018-12-25 | 2018-12-26 | 2018-12-26 | 2018-12-27 | 2018-12-27 | 2018-12-28 | 2018-12-28 | Ukończone (T) | Zaakceptowane (T/N)
#### | <Nazwa historyjki użytkownika> | Jako ____ chcę ____, więc ____. | Kiedy to robię, ____, dzieje się to: ____. | Wymaganie | 8 | Deweloper | 2018-12-24: 8; 2018-12-25: 8; 2018-12-26: 8; 2018-12-27: 8; 2018-12-28: 8
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
#### | <Nazwa historyjki użytkownika> | Jako ____ chcę ____, więc ____. | Kiedy to robię, ____, dzieje się to: ____. | Wymaganie | 5 | Deweloper | 2018-12-24: 5; 2018-12-25: 5; 2018-12-26: 5; 2018-12-27: 5; 2018-12-28: 5
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
#### | <Nazwa historyjki użytkownika> | Jako ____ chcę ____, więc ____. | Kiedy to robię, ____, dzieje się to: ____. | Wymaganie | 3 | Deweloper | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
#### | <Nazwa historyjki użytkownika> | Jako ____ chcę ____, więc ____. | Kiedy to robię, ____, dzieje się to: ____. | Wymaganie | 2 | Deweloper | 2018-12-24: 2; 2018-12-25: 2; 2018-12-26: 2; 2018-12-27: 2; 2018-12-28: 2
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
#### | <Nazwa historyjki użytkownika> | Jako ____ chcę ____, więc ____. | Kiedy to robię, ____, dzieje się to: ____. | Wymaganie | 1 | Deweloper | bar: 2018-12-24 to 2018-12-28
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
| <zadanie> | [5 empty] | 2018-12-24: 3; 2018-12-25: 3; 2018-12-26: 3; 2018-12-27: 3; 2018-12-28: 3
Rzeczywista liczba pozostałych godzin | [6 empty] | 2018-12-24: 120; 2018-12-25: 120; 2018-12-26: 120; 2018-12-27: 120; 2018-12-28: 120
Szacunkowa liczba pozostałych godzin | [6 empty] | 2018-12-24: 130; 2018-12-25: 97.5; 2018-12-26: 65; 2018-12-27: 32.5; 2018-12-28: 0
Pozostałe punkty historyjek | [6 empty] | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
[6 empty] | Day: | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5
Problemy
Członek zespołu
<problem>
Członek zespołu
<problem>
<problem>

## Rejestr sprintu - 2 tygodnie
<Nazwa produktu> - Sprint <#>
Daty sprintów: <Miesiąc> <DD> - <Miesiąc> <DD>, <RRRR>
[6 empty] | Dostępne godziny pracy w sprincie | [6 empty] | Dni w sprincie: |  | 10
Cel sprintu | [6 empty] | Pon. | Tu | Wt. | W | Śr. | Th | Czw. | F | Ptk. | M | Pon. | Tu | Wt. | W | Śr. | Th | Czw. | F | Ptk. | Łącznie
Zademonstruj umiejętność w zakresie <celu sprintu>. (UWAGA: Zdefiniuj cel sprintu pod względem działającej funkcjonalności klienta, którą będziesz w stanie zademonstrować wewnętrznym interesariuszom i ewentualnie wypuścić na rynek) | [5 empty] | Developerzy | 2019-11-25 | 2019-11-26 | 2019-11-26 | 2019-11-27 | 2019-11-27 | 2019-11-28 | 2019-11-28 | 2019-11-29 | 2019-11-29 | 2019-12-02 | 2019-12-02 | 2019-12-03 | 2019-12-03 | 2019-12-04 | 2019-12-04 | 2019-12-05 | 2019-12-05 | 2019-12-06 | 2019-12-06
[6 empty] | <Deweloper> | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 102
[6 empty] | <Deweloper> | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 102
[6 empty] | <Deweloper> | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 102
[6 empty] | <Deweloper> | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 102
[6 empty] | <Deweloper> | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 102
[7 empty] | 2019-11-29: Godziny sprintu łącznie:; 2019-12-06: Godziny sprintu łącznie: | 510
[7 empty] | 2019-11-29: Łącznie na dzień:; 2019-12-06: Łącznie na dzień: | 51
Feature Burndown - Based on estimated hours remaining
[7 empty] | Pon. | Tu | Wt. | W | Śr. | Th | Czw. | F | Ptk. | M | Pon. | Tu | Wt. | W | Śr. | Th | Czw. | F | Ptk.
ID | Zadanie |  |  | Typ | Punkty historyjek | Osoba odpowiedzialna | 2019-11-25 | 2019-11-26 | 2019-11-26 | 2019-11-27 | 2019-11-27 | 2019-11-28 | 2019-11-28 | 2019-11-29 | 2019-11-29 | 2019-12-02 | 2019-12-02 | 2019-12-03 | 2019-12-03 | 2019-12-04 | 2019-12-04 | 2019-12-05 | 2019-12-05 | 2019-12-06 | 2019-12-06 | Ukończone (T) | Zaakceptowane (T/N)
#### | <Nazwa historyjki użytkownika> | Jako ____ chcę ____, więc ____. | Kiedy to robię, ____, dzieje się to: ____. | Wymaganie | 8 | Deweloper | 2019-11-25: 8; 2019-11-26: 8; 2019-11-27: 8; 2019-11-28: 8; 2019-11-29: 8; 2019-12-02: 8; 2019-12-03: 8; 2019-12-04: 8; 2019-12-05: 8; 2019-12-06: 8
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
#### | <Nazwa historyjki użytkownika> | Jako ____ chcę ____, więc ____. | Kiedy to robię, ____, dzieje się to: ____. | Wymaganie | 5 | Deweloper | 2019-11-25: 5; 2019-11-26: 5; 2019-11-27: 5; 2019-11-28: 5; 2019-11-29: 5; 2019-12-02: 5; 2019-12-03: 5; 2019-12-04: 5; 2019-12-05: 5; 2019-12-06: 0; 2019-12-06: 5
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
#### | <Nazwa historyjki użytkownika> | Jako ____ chcę ____, więc ____. | Kiedy to robię, ____, dzieje się to: ____. | Wymaganie | 3 | Deweloper | 2019-11-25: 3; 2019-11-26: 3; 2019-11-27: 3; 2019-11-28: 3; 2019-11-29: 3; 2019-12-02: 3; 2019-12-03: 3; 2019-12-04: 3; 2019-12-05: 3; 2019-12-06: 0; 2019-12-06: 3
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
#### | <Nazwa historyjki użytkownika> | Jako ____ chcę ____, więc ____. | Kiedy to robię, ____, dzieje się to: ____. | Wymaganie | 2 | Deweloper | 2019-11-25: 2; 2019-11-26: 2; 2019-11-27: 2; 2019-11-28: 2; 2019-11-29: 2; 2019-12-02: 2; 2019-12-03: 2; 2019-12-04: 2; 2019-12-05: 2; 2019-12-06: 0; 2019-12-06: 2
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
#### | <Nazwa historyjki użytkownika> | Jako ____ chcę ____, więc ____. | Kiedy to robię, ____, dzieje się to: ____. | Wymaganie | 1 | Deweloper | 2019-11-25: 1; 2019-11-26: 1; 2019-11-27: 1; 2019-11-28: 1; 2019-11-29: 1; 2019-12-02: 1; 2019-12-03: 1; 2019-12-04: 1; 2019-12-05: 1; 2019-12-06: 0; 2019-12-06: 1
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
| <zadanie> | [5 empty] | 2019-11-25: 6; 2019-11-26: 6; 2019-11-27: 6; 2019-11-28: 6; 2019-11-29: 6; 2019-12-02: 6; 2019-12-03: 6; 2019-12-04: 6; 2019-12-05: 6; 2019-12-06: 6
Rzeczywista liczba pozostałych godzin | [6 empty] | 2019-11-25: 240; 2019-11-26: 240; 2019-11-27: 240; 2019-11-28: 240; 2019-11-29: 240; 2019-12-02: 240; 2019-12-03: 240; 2019-12-04: 240; 2019-12-05: 240; 2019-12-06: 240
Szacunkowa liczba pozostałych godzin | [6 empty] | 2019-11-25: 510; 2019-11-26: 453.3333; 2019-11-27: 396.6667; 2019-11-28: 340; 2019-11-29: 283.3333; 2019-12-02: 226.6667; 2019-12-03: 170; 2019-12-04: 113.3333; 2019-12-05: 56.6667; 2019-12-06: -4.2633e-14
Pozostałe punkty historyjek | [6 empty] | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
[6 empty] | Day: | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 10
Problemy
Członek zespołu
<problem>
Członek zespołu
<problem>
<problem>